## Phase 1 maturity trend (hidden)
Key enhancements:
KPI aggregation
UAT #1 bug fixes for wind
Key enhancements:
KPI aggregation
UAT #1 bug fixes for solar
Key enhancements:
manual upload of table tilting
manual upload of module cleaning
manual upload of grass cutting
Auto reports
Bugs related to SAP integration.
Key enhancements:
breakdown pie-chart summaries
daily dgr status mails
ad-hoc reporting

## Phase 1&2 maturity trend (hidden)
Key enhancements:
KPI aggregation
UAT #1 bug fixes for wind
Key enhancements:
KPI aggregation
UAT #1 bug fixes for solar
Key enhancements:
manual upload of table tilting
manual upload of module cleaning
manual upload of grass cutting
Auto reports
Bugs related to SAP integration.
Key enhancements:
breakdown pie-chart summaries
daily dgr status mails
ad-hoc reporting

## IC NOC AGEL Phase 1 - UAT Score
|  |  | 3580 | 2685 | [5 empty] | 46.65% |  | 1670 |  |  |  | 3580 | 26.17% |  | 937 | 34.9%
S No. | Requirements | Solar / Wind | Max. marks | Project Phase | Dev Status | UAT A Test Steps | UAT B Test Steps | Test Video Link/Initial Comments | Internal UAT - Ownership | Internal UAT Closure Date | UAT Outcome 0 - Failed, Not offered 0.5-Partially Passed (Platform + Data) 0.75 - Partially Passed (Data only) 1-Passed | Internal Marks Obtained | Target date for achieving Full Functionality Score | Internal UAT-A Pass/Fail Status for BU UAT | Tickets to be resolved for Phase 1 - Raised by Project Team | Business User for UAT | Business UAT Closure Date for functionality with bug closure | Business UAT Outcome 0 - Failed, Not offered 0.5-Partially Passed (Platform + Data) 0.75 - Partially Passed (Data only) 1-Passed | Business UAT Marks Obtained | Business UAT-A Pass/Fail Status | Tickets to be resolved for Phase 1 - Raised by BU | Issue (Platform / Source Data) | Business Requirement Considered for Phase 1 | Business Requirement to be considered for Phase 2 | ICNOC Comment | ENOC Remarks
| Solar |  |  | NA | NA
| Portfolio, SPV, State & Plant Level (Aggregation Configurable) |  |  | NA | NA
1 | Power vs Radiation Curve | Solar | 8 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select any asset level: Portfolio/SPV/RG/State/Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Active Power vs Radiation" from Thumbnails 7. Click on Run | 1. Verify the NOC data that can be downloaded from the graph and compare with the sitewise SCADA sample data for Active Power (MW) 2. Verify the NOC data that can be downloaded from the graph and compare with the sitewise SCADA sample data for Irradiation (W/m2) | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/01.%20Active%20Power%20vs%20Irradiation.mp4 | Hardik |  | 0.75 | 6 | 2021-10-23 | Pass |  | Aaron | 2021-10-30 | 0.5 | 4 | Fail | ICNOC-1081 ICNOC-1155 ICNOC-1156 | Platform | 1. Curves to be available at Portfolio, SPV, State and Plant Level | 1. Pan, Zoom In and Zoom Out required with Reset 2. Peak Power and Peak Irradiation to be mentioned | Only availbale at the plant level. Development at logical grouping is under progress | Peak value of irradiation cant be see an ZOOM IN feature not available or 1 hour high resolution data not available Portfolio level Active power vs IRR curve not correct. SPV, Portfolio is not visible
2 | Net Export and radiation trend - Budget vs Actual (MTD & YTD) | Solar | 12 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select any asset level: Portfolio/SPV/RG/State/Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Net Export vs Irradiation" from Thumbnails 7. Click on Run | 1. Verify the NOC data that can be downloaded from the graph and compare with the sitewise site MIS data for Net Export (MWh) 2. Verify the NOC data that can be downloaded from the graph and compare with the sitewise site MIS data for Irradiation (kWh) | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/02.%20Net%20Export%20vs%20Radiation%20Trend.mp4 | Hardik |  | 0.75 | 9 | 2021-10-23 | Pass |  | Jamuvant | 2021-10-30 | 0.75 | 9 | Partially Passed | ICNOC 1082 | Platform | 1. Plots to be available at Portfolio, SPV, State and Plant Level 2. Budget vs Actual Trend to be seen 3. MTD and YTD values to be seen | 1. Pan, Zoom In and Zoom Out required with Reset | Only availbale at the plant level. Development at logical grouping is under progress | YTD not available Zoom in zoom out feature not available specifically required while analysing multiple days
3 | Net Export vs Expected generation | Solar | 8 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select any asset level: Portfolio/SPV/RG/State/Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Net Export vs Expected Generation" from Thumbnails 7. Click on Run | 1. Verify the NOC data that can be downloaded from the graph and compare with the sitewise site MIS data for Net Export (MWh) 2. Verify the NOC data that can be downloaded from the graph and compare with the sitewise site MIS data for Budget Generation (MWh) | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/03.%20Net%20Export%20vs%20Expected%20Gen.mp4 | Hardik |  | 0.75 | 6 | 2021-10-23 | Pass |  | Tushar | 2021-10-30 | 0.75 | 6 | Partially Passed | ICNOC 1083 ICNOC-1183 | Platform | 1. Plots to be available at Portfolio, SPV, State and Plant Level | 1. Pan, Zoom In and Zoom Out required with Reset | Only availbale at the plant level. Development at logical grouping is under progress | Zoom in zoom out feature not available specifically required while analysing multiple days
4 | CUF - Budget vs Actual (day wise, month wise and year wise trend) | Solar | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select any asset level: Portfolio/SPV/RG/State/Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "CUF PPA (Actual vs Budget)" from Thumbnails 7. Click on Run | 1. Verify the NOC data that can be downloaded from the graph and compare with the sitewise site MIS data for CUF PPA (%) 2. Verify the NOC data that can be downloaded from the graph and compare with the sitewise site MIS data for Budget CUF PPA (%) | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/04.%20CUF%20(Budget%20vs%20Actual).mp4 | Hardik |  | 0.75 | 15 | 2021-10-23 | Pass |  | Tushar | 2021-10-30 | 0.75 | 15 | Partially Passed | ICNOC 1084 ICNOC-1184 |  | 1. Plots to be available at Portfolio, SPV, State and Plant Level 2. Day wise, Monthwise and Year wise granularity should be available | 1. Pan, Zoom In and Zoom Out required with Reset | Only availbale at the plant level. Development at logical grouping is under progress | Daywise : The graph is very bulky. Also the budget Axis and Actual data axis is mismatch YTD : Data not correct YTD trend not visible
4.1 | CUF - Weather Corrected from PVSyst (day wise, month wise and year wise trend) | Solar | 20 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0 |  |  |  | 1. Plots to be available at Portfolio, SPV, State and Plant Level 2. Day wise, Monthwise and Year wise granularity should be available | 1. Pan, Zoom In and Zoom Out required with Reset | PV Syst Integration
5 | Performance Ratio - Budget vs Actual (day wise, month wise and year wise trend) | Solar | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select any asset level: Portfolio/SPV/RG/State/Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Performance Ratio (Actual vs Budget)" from Thumbnails 7. Click on Run | 1. Verify the NOC data that can be downloaded from the graph and compare with the sitewise site MIS data for PR (%) 2. Verify the NOC data that can be downloaded from the graph and compare with the sitewise site MIS data for Budget PR (%) | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/05.%20PR%20(Budget%20vs%20Actual).mp4 | Hardik |  | 0.75 | 15 | 2021-10-23 | Pass |  | Mihir | 2021-10-30 | 0.75 | 15 | Partially Passed | ICNOC-959 ICNOC-962 ICNOC-963 ICNOC-1164 |  | 1. Plots to be available at Portfolio, SPV, State and Plant Level 2. Day wise, Monthwise and Year wise granularity should be available | 1. Pan, Zoom In and Zoom Out required with Reset | To be extended to the logical grouping | Daywise : The graph is very bulky. Also the budget Axis and Actual data axis is mismatch YTD : Data not correct YTD trend not visible
5.1 | Performance Ratio - Weather Corrected from PVSyst (day wise, month wise and year wise trend) | Solar | 20 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0 |  |  |  | 1. Plots to be available at Portfolio, SPV, State and Plant Level 2. Day wise, Monthwise and Year wise granularity should be available | 1. Pan, Zoom In and Zoom Out required with Reset | PV Syst Integration
6 | Plant Availability - Time based and Generation weighted (day wise, month wise and year wise trend) | Solar | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select any asset level: Portfolio/SPV/RG/State/Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Plant Availability Trend" from Thumbnails 7. Click on Run |  |  | Hardik |  | 0.5 | 10 | 2021-11-27 | Yet to test |  |  | 2021-12-04 |  | 0 |  | ICNOC-964 ICNOC-966 ICNOC-971 |  | 1. Plots to be available at Portfolio, SPV, State and Plant Level 2. Day wise, Monthwise and Year wise granularity should be available 3. Time based plant availability | 1. Pan, Zoom In and Zoom Out required with Reset 2. Generation based plant availability needed | To be extended to the logical grouping | YTD trend not visible
7 | Grid Availability (Outage and Curtailment) - Time based and Generation weighted (day wise, month wise and year wise trend) | Solar | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select any asset level: Portfolio/SPV/RG/State/Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Grid Availability (Actual vs Budget)" from Thumbnails 7. Click on Run | 1. Verify the NOC data that can be downloaded from the graph and compare with the sitewise site MIS data for Grid Availability (%) | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/11.%20Grid%20Availability%20(Budget%20vs%20Actual).mp4 | Hardik |  | 0.75 | 15 | 2021-10-23 | Pass |  | Jamuvant | 2021-10-30 | 0.75 | 15 | Partially Passed | ICNOC-970 ICNOC-971 | Know source data issue. KPI formula change is required by business. Voltages are not correctly for Nalgonda, Minpur and Siddipet site | 1. Plots to be available at Portfolio, SPV, State and Plant Level 2. Day wise, Monthwise and Year wise granularity should be available | 1. Pan, Zoom In and Zoom Out required with Reset | To be extended to the logical grouping | YTD trend not visible
8 | Equipment Availability (Inverter, string, IDT, Switchgear, Switchyard, RMU, ODU, LT Panel, HT cable, MCCB, ACSB,LT cable, tracker) - Time based and Generation weighted (day wise, month wise and year wise trend, make wise ) | Solar | 40 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In KPI tab, from Asset Explorer section In Solar Power Plants -select any asset level: Portfolio/SPV/RG/State/Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Equipment Availability" from Thumbnails 7. Click on Run Make wise would be considered in Phase 2 | 1. Verify the NOC data that can be downloaded from the graph and compare with the sitewise site MIS data for Availability (%) |  | Hardik |  | 0.5 | 20 | 2021-11-27 | Yet to test |  |  | 2021-12-04 |  | 0 |  | ICNOC-1011 | Source | 1. Plots to be available at Portfolio, SPV, State and Plant Level 2. Day wise, Monthwise and Year wise granularity should be available 3. Time based availability | 1. Pan, Zoom In and Zoom Out required with Reset 2. Generation based plant availability needed | To be extended to the logical grouping | YTD trend not visible; Availability for tracker not available ,values of availability are not correct.
9 | Irradiation - Budget vs Actual (day wise, month wise and year wise trend) | Solar | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select any asset level: Portfolio/SPV/RG/State/Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Irradiation (Actual vs Budget)" from Thumbnails 7. Click on Run | 1. Verify the NOC data that can be downloaded from the graph and compare with the sitewise site MIS data for Irradiation (kWh) 2. Verify the NOC data that can be downloaded from the graph and compare with the sitewise site MIS data for Budget Irradiation (kWh) | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/06.%20Irradiation%20(Budget%20vs%20Actual).mp4 | Hardik |  | 0.75 | 15 | 2021-10-23 | Pass |  | Aaron | 2021-10-30 | 0.75 | 15 | Partially Passed | ICNOC-1009 ICNOC-1158 | Platform | 1. Plots to be available at Portfolio, SPV, State and Plant Level 2. Budget vs Actual Trend to be seen 3. Day wise, Monthwise and Year wise granularity should be available | 1. Pan, Zoom In and Zoom Out required with Reset | To be extended to the logical grouping | YTD trend not visible
10 | Specific Yield - Budget vs Actual (day wise, month wise and year wise trend) | Solar | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select any asset level: Portfolio/SPV/RG/State/Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Specific Yield (Actual vs Budget)" from Thumbnails 7. Click on Run | 1. Verify the NOC data that can be downloaded from the graph and compare with the sitewise site MIS data for Specific Yield (kWh/kWp) 2. Verify the NOC data that can be downloaded from the graph and compare with the sitewise site budget data for Budget Specific Yield (kWh/kWp) | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/07.%20Specific%20Yield%20(Budget%20vs%20Actual).mp4 | Hardik |  | 0.75 | 15 | 2021-10-23 | Pass |  | Aadil | 2021-10-30 | 0.75 | 15 | Partially Passed | ICNOC-1037 |  | 1. Plots to be available at Portfolio, SPV, State and Plant Level 2. Budget vs Actual Trend to be seen 3. Day wise, Monthwise and Year wise granularity should be available | 1. Pan, Zoom In and Zoom Out required with Reset |  | YTD trend not visible
11 | Revenue - Budget vs Actual | Solar | 12 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select any asset level: Portfolio/SPV/RG/State/Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Revenue (Actual vs Budget)" from Thumbnails 7. Click on Run | 1. Verify the NOC data that can be downloaded from the graph and compare with the sitewise site MIS data for Revenue (INR Cr.) 2. Verify the NOC data that can be downloaded from the graph and compare with the sitewise site MIS data for BudgetRevenue (INR Cr.) | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/08.%20Revenue%20(Budget%20vs%20Actual).mp4 | Hardik |  | 0.75 | 9 | 2021-10-23 | Pass |  | Aadil | 2021-10-30 | 0.75 | 9 | Partially Passed | ICNOC-988 |  | 1. Plots to be available at Portfolio, SPV, State and Plant Level 2. Budget vs Actual Trend to be seen | 1. Pan, Zoom In and Zoom Out required with Reset | To be extended to the logical grouping | Not available at SPV, Portfolio
12 | Generation loss/gain due to irradiation shortfall/gain | Solar | 8 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select any asset level: Portfolio/SPV/RG/State/Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Generation loss/gain due to irradiation shortfall/gain" from Thumbnails 7. Click on Run | 1. Compare the data from the NOC Gen loss/gain due to irradiation shortfall/gain with the sample wise data from site | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/12.%20Gen%20Gain-Loss%20due%20to%20Irradiation.mp4 | Hardik |  | 0.75 | 6 | 2021-10-23 | Pass |  | Subrat | 2021-10-30 | 0.75 | 6 | Partially Passed | ICNOC 1012 ICNOC-1172 ICNOC-1173 ICNOC-1174 |  | 1. Plots to be available at Portfolio, SPV, State and Plant Level | 1. Pan, Zoom In and Zoom Out required with Reset | To be extended to the logical grouping | Not available at Logical Level Widget is sometimes not loading
13 | Generation loss due to Plant Unavailability (As per actual irradiation) | Solar | 8 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select any asset level: Portfolio/SPV/RG/State/Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Generation loss due to Plant Unavailability (As per actual irradiation)" from Thumbnails 7. Click on Run | 1. Compare the data from the NOC Generation loss due to Plant Unavailability (As per actual irradiation) with the sample wise data from site MIS |  | Hardik |  | 0.5 | 4 | 2021-11-27 | Yet to test |  |  | 2021-12-04 |  | 0 |  | ICNOC 1015 |  | 1. Plots to be available at Portfolio, SPV, State and Plant Level |  | To be extended to the logical grouping | Not available at Logical Level Not visible in events timeline
14 | Generation loss/gain due to DC capacity less/ high than design | Solar | 8 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select any asset level: Portfolio/SPV/RG/State/Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Gen Loss/Gain due to DC Capacity less/high than design" from Thumbnails 7. Click on Run | 1. Compare the data from the NOC Generation loss/gain due to DC capacity less/ high than design with the sample wise data from site | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/13.%20Gen%20Loss%20due%20to%20DC%20Capacity.mp4 | Hardik |  | 0.75 | 6 | 2021-10-23 | Pass |  | Subrat | 2021-10-30 | 0.75 | 6 | Partially Passed | ICNOC-1085 ICNOC-1175 |  | 1. Plots to be available at Portfolio, SPV, State and Plant Level |  | To be extended to the logical grouping | Not available at Logical Level
15 | Generation loss due to Grid outage ad curtailment (As per actual irradiation) | Solar | 8 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select any asset level: Portfolio/SPV/RG/State/Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Gen Loss/Gain due to grid outage and curtailment" from Thumbnails 7. Click on Run | 1. Select the day where there is grid curtailment / downtime 2. Verify the selected analysis data with site MIS / DGR report | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/23.%20Loss%20due%20to%20Grid%20Unavailability%20-%20Solar.mp4 | Hardik |  | 0.75 | 6 | 2021-10-30 | Pass |  | Aaron Kalisha | 2021-11-06 | 0.75 | 6 | Partially Passed | ICNOC-993 ICNOC-1234 |  | 1. Plots to be available at Portfolio, SPV, State and Plant Level |  | To be extended to the logical grouping | Not available at Logical Level Not visible in events timeline
16 | Generation loss due to shadow (pitch, adjacent table, object) | Solar | 8 | MVP 02 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select any asset level: Portfolio/SPV/RG/State/Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Gen Loss/Gain due to shadow" from Thumbnails 7. Click on Run Note: Values would alway be 0 as the plant configured in GCP do not have any shadow loss configuration info from business. Currently we have info only for Channapatna, Gubbi, KR Pete, Magadi, Tiptur, Narsipura, Ramnagara |  |  | Hardik |  | 0.75 | 6 | 2021-10-30 | Pass | ICNOC-1161 | Darshak | 2021-11-06 | 1 | 8 | Pass |  |  | 1. Plots to be available at Portfolio, SPV, State and Plant Level |  | Under development | Due to non-availability of Shadow loss we are unable to verify the Generation loss due to shadow
17 | Generation loss due to excessive soiling | Solar | 8 | MVP 02 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select any asset level: Portfolio/SPV/RG/State/Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Gen Loss/Gain due to excessive soiling" from Thumbnails 7. Click on Run |  |  | Hardik |  | 0.75 | 6 | 2021-10-30 | Pass | ICNOC-1210 | Jamuvant | 2021-11-06 | 0.75 | 6 | Partially Passed |  |  | 1. Plots to be available at Portfolio, SPV, State and Plant Level |  | Under development | 1. In the Analysis catalog, while selecting the KPI/Analysis, releated analysis/KPI should be visible. For example, if the user has selected Gen loss due to excessive soiling Analysis, then he should also get to see the % soiling loss, that would help to correlate. Like in QoS, formula implemented should be visible that should atleast include a) Business Formula b) High level code c) Tags / other KPI used for this KPI or analysis
18 | Generation loss due to excess AC loss | Solar | 8 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select any asset level: Portfolio/SPV/RG/State/Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Gen Loss/Gain due to excessive AC Loss" from Thumbnails 7. Click on Run |  | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/24.%20Gen%20Loss%20due%20to%20Excessive%20AC%20Loss.mp4 | Hardik |  | 0.75 | 6 | 2021-10-30 | Pass |  | Aadil Khan | 2021-11-06 | 1 | 8 | Pass | ICNOC-1008 |  | 1. Plots to be available at Portfolio, SPV, State and Plant Level |  | To be extended to the logical grouping
19 | Generation loss/gain on account of module temperature | Solar | 8 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0 |  |  |  | 1. Plots to be available at Portfolio, SPV, State and Plant Level |  | PV Syst Integration
20 | Generation loss due to excessive module degradation | Solar | 8 | MVP 02 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select any asset level: Portfolio/SPV/RG/State/Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Gen Loss/Gain due to excessive module degradation" from Thumbnails 7. Click on Run |  | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/25.%20Loss%20due%20to%20excessive%20module%20degradation.mp4 | Hardik |  | 0.75 | 6 | 2021-10-30 | Pass |  | Jamuvant | 2021-11-06 | 0.5 | 4 | Fail | ICNOC-1229 |  | 1. Plots to be available at Portfolio, SPV, State and Plant Level |  | Under development
21 | CUF bridge (Waterfall diagram showing actual and budgeted CUF and revenue and impact in CUF and revenue of all the losses mentioned above) | Solar | 40 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select any asset level: Portfolio/SPV/RG/State/Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "CUF Bridge" from Thumbnails 7. Click on Run Note: Components like Loss due to module temp would be available in Phase 2 as it is linked with PVsyst integration |  | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/26.%20Solar%20CUF%20Bridge.mp4 | Hardik |  | 0.75 | 30 | 2021-10-30 | Pass | ICNOC-1214 |  | 2021-11-06 |  | 0 |  | ICNOC-1007 |  | 1. CUF Bridge to be available at Portfolio, SPV, State and Plant Level 2. Daily CUF bridge should also be visible | 1. Components to be added in CUF bridge dependent on Pvsyst integration i.e. CUF Loss due to module temperature 2. When Gap is identified - if positive value, value should show above the bar, if negative below the bar | Rest 3-4 remaining components were part of MVP02 | Daily CUF Bridge is not available.All components are not visible in bridge;even if under developement we can atleast show the bridge with all the components the value can be zero. The aesthetic look of the bridge at first glance is not impressive attaching expected feature look in ENOC Expectation column. Logical Grouping CUF bridge not available. Same points applicable for revnue bridge as well.
22 | Component - wise generation loss (Inverter, string, IDT, Switchgear, Switchyard, RMU, ODU, LT Panel, HT cable, LT cable, tracker, DC cable)(day wise, month wise and year wise trend, make wise, fault wise loss ) | Solar | 40 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select any asset for which generation loss is required 4. Click on Catalog 5. Select the date range 6.Select mentioned "Generation Loss" from Thumbnails 7. Click on Run |  |  | Hardik |  | 0.5 | 20 | 2021-11-27 | Yet to test |  |  | 2021-12-04 |  | 0 |  | ICNOC-1033 |  | 1. Plots to be available at Portfolio, SPV, State, Plant & respective equipment Level 2. Day wise, Monthwise and Year wise granularity should be available | 1. Tracker availability & its generation loss | To be extended to the logical grouping | Component wise Gen loss is not available. Gen loss due to plant,Grid trip,Curtailment,Excess AC and DC shortfall is available. year wise trend, make wise, fault wise loss is not availalbe. New Enhancement: At plant level all the loss as per component wise to be shown in the single screen
23 | Tracker angle deviation (w.r.t. average) | Solar | 4 | MVP 02 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select the tracker or set of tracker for which we need to plot the tracker angle 4. Click on Catalog 5. Select the date range 6.Select mentioned "Tracker Angle Deviation" from Thumbnails 7. Click on Run |  |  | Hardik |  | 0.5 | 2 | 2021-11-13 | Yet to test |  |  | 2021-11-20 |  | 0 |  | ICNOC-1061 |  | 1. To be available at block and equipment level | 1. Deviation angle trend to be implemented based on a reference file |  | Deviation angle trend to be implemented based on a reference file (to be checked against original reqs, new enhancement?)
24 | Block PR | Solar | 4 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In KPI tab, from Asset Explorer section In Solar Power Plants -select the block of the plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Block PR" from Thumbnails 7. Click on Run |  | Not able to see | Hardik |  | 0.75 | 3 | 2021-10-30 | Pass | ICNOC-1220 | Darshak | 2021-11-06 | 0.75 | 3 | Partially Passed |  |  | 1. To be available at the block level |  | Source Data issue for plant except Ghani
25 | Inverter PR deviation histogram (Median - top 10 performing inverters & average PR of all inverters) | Solar | 40 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In KPI tab, from Asset Explorer section In Solar Power Plants -select the plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Inverter PR deviation band" from Thumbnails 7. Click on Run |  |  | Hardik |  | 0.75 | 30 | 2021-10-30 | Pass | ICNOC-1214 |  | 2021-11-06 |  | 0 |  | ICNOC-1058 |  | 1. To be available at the plant level | 1. Report must include the bottom 10 performing inverters where "10" is a user configurable no. |  | New Enhancement: Top 10 inverters also to be shown in the same template
26 | Inverter normalized power (KW/KWp) trend | Solar | 4 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select the portfolio, SPV, State, Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Inverter Normalized Power" from Thumbnails 7. Click on Run |  |  | Hardik |  | 0.5 | 2 | 2021-11-13 | Fail | ICNOC-1215 |  | 2021-11-20 |  | 0 |  |  |  | 1. To be available at the plant level 2. Multiple Inverters should be selected and be able to plot
27 | Inverter specific yield (KWh/KWp) | Solar | 4 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In KPI tab, from Asset Explorer section In Solar Power Plants -select the portfolio, SPV, State, Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Inverter Specific Yield" from Thumbnails 7. Click on Run |  | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/27.%20Inverter%20Specific%20Yield.mp4 | Hardik |  | 0.75 | 3 | 2021-10-30 | Pass |  | Mihir Patel | 2021-11-06 | 0.75 | 3 | Partially Passed | ICNOC-1059 ICNOC-1060 ICNOC-1246 |  | 1. To be available at the plant, block and inverter level 2. Multiple Inverters should be selected and be able to plot |  |  | Multiple asset selection should provide individual curves; block level SY to be checked (based in IDT vs Inverter aggregation) si this new enhancement because of lack of MFM in new plants
28 | Inverter PR | Solar | 4 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In KPI tab, from Asset Explorer section In Solar Power Plants -select the portfolio, SPV, State, Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Inverter PR" from Thumbnails 7. Click on Run |  | Not able to see | Hardik |  | 0.5 | 2 | 2021-11-06 | Fail | ICNOC-1133 |  | 2021-11-13 |  | 0 |  | ICNOC-1062 |  | 1. To be available at the plant, block and inverter level 2. Multiple Inverters should be selected and be able to plot |  |  | Multiple asset selection should provide individual curves; block level SY to be checked (based in IDT vs Inverter aggregation) si this new enhancement because of lack of MFM in new plants
29 | String PR deviation histogram (Median - top 10 performing strings) | Solar | 40 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In KPI tab, from Asset Explorer section In Solar Power Plants -select the plant with string inverters 4. Click on Catalog 5. Select the date range 6.Select mentioned "String PR deviation band" from Thumbnails 7. Click on Run |  | Not able to see | Hardik |  | 0.75 | 30 | 2021-11-13 | Pass | ICNOC-1241 |  | 2021-11-20 |  | 0 |  | ICNOC-1038 |  | 1. To be available at the plant level | 1. Require the string PR histogram report which shows low performing strings |  | New report to be created - string PR in line with what we’ve done for Inverter PR
30 | String PR | Solar | 4 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In KPI tab, from Asset Explorer section In Solar Power Plants -select the Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "String PR" from Thumbnails 7. Click on Run | 1. Compare the data from the NOC string PR with the sample wise data from site | Not able to see | Hardik |  | 0.5 | 2 | 2021-11-13 | Fail | ICNOC-1146 |  | 2021-11-20 |  | 0 |  | ICNOC-1025 |  | 1. To be available at the plant, block, inverter and string level 2. Multiple strings should be selected and be able to plot |  |  | Multiple asset selection should provide individual curves; block level SY to be checked (based in IDT vs Inverter aggregation) si this new enhancement because of lack of MFM in new plants
31 | String Power trend | Solar | 4 | MVP 02 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select the Strings 4. Click on Catalog 5. Select the date range 6. Select 5 min granularity 7.Select mentioned "String Power trend" from Thumbnails 8. Click on Run | 1. Compare the data from the NOC string power tend with the sample wise data from site | Not able to see | Hardik |  | 0.5 | 2 | 2021-11-13 | Fail | ICNOC-1240 |  | 2021-11-20 |  | 0 |  |  |  | 1. To be available at the inverter and string level 2. Multiple strings should be selected and be able to plot
32 | Provision for manual data (module cleaning, grass cutting, table tilting) input | Solar | 20 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0 |  |  |  | 1. User should be able to upload data for module cleaning, grass cutting and table tilting
33 | 5x5 matrix (frequency rating vs severity rating) at plant level and equipment level, considering severity as: a. Generation loss | Solar | 20 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0 |  | ICNOC-1018 |  | 1. Able to see the plant level 5x5 matrix at plant and inverter level | 1. User should be able to see the events related to the each entry in the 5x5 matrix from the same plot/widget/screen | HT and LT Cable Availability to be added to the matrix Equipment level is pending | New enhancement - user should be able to see the events that contributed to each category, can be a report
34 | Generation loss due to late awakening inverters/early sleeping inverters. | Solar | 8 | MVP 02 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Reports tab, from Asset Explorer section In Solar Power Plants -select the plant for which user needs this report 4. Click on Reports tab 5. Select the date range 6.Select mentioned report "Generation loss due to late awakening inverters/early sleeping inverters" from Thumbnails 7. Click on Run 8. As a part of the report user must be able to see the generation , loss due to late awakening and early sleeping |  | Report is not loading | Hardik |  | 0.75 | 6 | 2021-11-13 | Pass | ICNOC-1180 |  | 2021-11-20 |  | 0 |  |  |  | 1. Should be available at the plant level
35 | IV curve of strings | Solar | 10 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
36 | Change in Plant Configuration details (DC addition/deletion, Inverter addition/deletion/change in name & serial number at block level and plant level) | Solar | 10 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | Inverter change in AMM screen pending | The functionality exists from the backend front-end user facing function will come with asset management screens
37 | Change in a breakdown type | Solar | 20 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
38 | Equipment level MTTR & MTBF calculation. | Solar | 10 | MVP 02 | In Prod | 1. Go to the Tickets Workspace from the navigation bar 2. Select last 30 days as the date range so that some tickets get populated 3. Go to the MTTR tab and select any plant in the MTTR panel 4. In the next panel select an equipment with one or more tickets shown in front of it 5. The MTTR for the equipment will be shown in the last panel (in case you don't see anything, click on "benchmark" below the graph to turn it off and rescale the graph to show only actual MTTR values 6. In the table below, scroll to the right to show the TTR column 7. Calculate the average TTR and compare with the TTR shown in the graph above 8. The MTTR shown in the graph and the calculated average TTR should match each other |  |  | Utkarsh |  | 0.5 | 5 | 2021-11-27 | Yet to test |  |  | 2021-12-04 |  | 0 |  | ICNOC-1016 |  |  |  |  | Not available at Logical Level, this will not be solved with the global logical level work, will need custom dev. This feature is based on maintenance tickets in SAP PM (preventive maintenance is not included in this)
39 | Provision for uploading SOP, drawing, (files & folders) | Solar | 10 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
40 | Rules to be made to distinguish between Data unavailability and erroneous data | Solar | 20 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | It is already there as a part of data quality screen | UAT to be done with the SCADA team. Data availability report is under dev
41 | Scorecard as per user defined rule | Solar | 10 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
42 | KPI comparison across various sites/group level/ portfolio level | Solar | 12 | MVP 01 | In Prod | 1. Login with accepted credentials for NOC Portal. 2.From Left Navigation bar in Analysis section click on Analysis Catalog screen 3 By default the date would be of present day and based on this day the graph will be shown 4.User can also change the date range in Date filter present on the page 5. By default KPI section will get open and user will select options from dropdown present in Asset Explorer section The user can select by expanding AGEL for eg: expand Solar GHANI then Expand BLOCK then expand BLK01 then select any of the option from the expanded dropdown as parent selection wont work so user needs to expand the chain and select child asset 6. Click on Catalog option on top left 7.Select any of the Thumbnail of graph for eg: Total Generation present in the catalog section, The Run button will enable only when user will select the thumbnail 8.Click on Run Button and the user will be able to see the selected thumbnail graph for the selected asset in Asset Explorer on right side of the page 9.Repeat these steps for all other KPIs,assets and catalogs present here for different plants, logical grouping levels |  |  | Hardik |  | 0.75 | 9 | 2021-10-23 | Pass |  | Darshak | 2021-10-30 | 0.75 | 9 | Partially Passed | ICNOC-1179 ICNOC-1181 | Platform
43 | Inverter guaranteed uptime calculation as per contractual term for different make (terms provided by adani) | Solar | 20 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
44 | Specific widget at portfolio level(showing no. of plant running & no. of plant under breakdown, at plant level showing no. of block running & no. of block under breakdown & no. of inverters running & breakdown) | Solar | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Portfolio Drill Down Screen 3. Select the plant which the user wants to drill down 4. Select the Block in case of solar and WTG in case of wind for which drill down is req. 5. Select the tag in the drill down screen which the user wants to see 6. Test the functionality of creating a Ticket using "Create Ticket" button 7. Test the functinality of landing to the Analysis Catalog using "Analysis" button |  | Not able to create the ticket from portfolio drill down screen | Hardik |  | 0.75 | 15 | 2021-10-23 | Pass |  | Mihir | 2021-10-30 | 0.5 | 10 | Fail | ICNOC-1166 | Ready for Retest |  |  |  | Number of plants running / in breakdown / out of comm, to be checked if the feature is avl in BAX and the scores will be revised accordingly
45 | Inverter efficiency at portfolio level for different make | Solar | 20 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | Part of PTD
46 | MPPT level power, voltage, current | Solar | 12 | MVP 02 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Tags tab, from Asset Explorer section In Solar Power Plants -select any Inverter (max. 150 asset) 4. Click on Tags 5. Select the date range 6.Select the required tag 7. Click on Run 8.Verify the functionality of downloading the data in csv file 9.Verify the zoom (snip & zoom) in and reset zoom functionality | 1. Download and verify the data from the site TML file | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/09.%20MPPT%20Power,%20Voltage%20&%20Current.mp4 | Hardik |  | 1 | 12 | 2021-10-23 | Pass |  | Jamuvant | 2021-10-30 | 0.75 | 9 | Partially Passed |  | Source - MPPT tag data for plant other than Ghani to be added by SCADA team |  |  | Part of Tags section
47 | WTI alarm, OTI alarm, MOG alarm, Bucholz alarm should automatically emailed to specific persons | Solar | 20 | MVP 02 | In Prod | Note - This requires the email ID and role of the person receiving the email to be setup correctly, for any site where this is to be tested, please provide your email IDs to the program team (Utkarsh, Tapan, Hardik) so that email notifications can be enabled for the users. Once this setup is done - 1. Create a WTI / OTI / MOG / Bucholz alarm from the SCADA system (this will need to be done incase actual alarms are not available in the system) 2. This alarm will get captured by NOC and the email alert will get triggered 3. Correctly setup users can check the alarm notification in thier email inbox 4. Please note that the user should be setup for the same site where the alarm is created |  |  | Utkarsh |  | 0.5 | 10 | 2021-11-06 | Yet to test |  |  | 2021-11-13 |  | 0 | [5 empty] | Part of Workflow
| Block Level |  |  | NA | NA
1 | Power vs Radiation Curve | Solar | 8 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select any block of the particular plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Active Power vs Radiation" from Thumbnails 7. Click on Run |  |  | Hardik |  | 0.75 | 6 | 2021-10-30 | Pass | ICNOC-1225 | Jamuvant | 2021-11-06 | 1 | 8 | Pass | [5 empty] | not visible
2 | Net Export and radiation trend - Budget vs Actual (MTD & YTD) | Solar | 12 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select any block of the particular plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Net Export and radiation trend - Budget vs Actual" from Thumbnails 7. Click on Run |  |  | Hardik |  | 0.5 | 6 | 2021-11-20 | Fail | ICNOC-1226 |  | 2021-11-27 |  | 0 | [6 empty] | not visible
3 | Net Export vs Expected generation | Solar | 8 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select any block of the particular plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Net Export vs Expected Generation" from Thumbnails 7. Click on Run |  |  | Hardik |  | 0.75 | 6 | 2021-10-30 | Pass | ICNOC-1227 | Jamuvant | 2021-11-06 | 0.75 | 6 | Partially Passed | ICNOC-1314 |  |  |  |  | not visible
4 | CUF - Budget vs Weather Corrected vs Actual (day wise, month wise and year wise trend) | Solar | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select any block of the particular plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "CUF Budget vs Actual" from Thumbnails 7. Click on Run |  | Not able to see it at block level | Hardik |  | 0.75 | 15 | 2021-10-30 | Pass | ICNOC-1135 | Jamuvant | 2021-11-06 | 0.75 | 15 | Partially Passed | ICNOC-1315 |  |  |  |  | not visible
5 | Performance Ratio - Budget vs Weather Corrected vs Actual (day wise, month wise and year wise trend) | Solar | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select any block of the particular plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "PR Budget vs Actual" from Thumbnails 7. Click on Run |  | Not able to see it at block level | Hardik |  | 0.75 | 15 | 2021-10-30 | Pass | ICNOC-1135 | Jamuvant | 2021-11-06 | 0.75 | 15 | Partially Passed | ICNOC-1316 |  |  |  |  | not visible
6 | Inverter normalized power (KW/KWp) trend | Solar | 4 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select any block of the particular plant 4. Click on Catalog 5. Select the single day for which the user wants to see the trend 6.Select mentioned "Inverter Normalized Power" from Thumbnails 7. Click on Run |  | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/37.%20Inverter%20Normalized%20Power.mp4 | Hardik |  | 0.75 | 3 | 2021-10-30 | Pass |  | Aaron Kalisha | 2021-11-06 | 0.75 | 3 | Partially Passed |  |  |  |  | To be extended to the logical grouping | 1. Aggregation is not correct
7 | Inverter specific yield (KWh/KWp) | Solar | 4 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select any block/or multiple blocks of the particular plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Inverter Specific Yield" from Thumbnails 7. Click on Run |  | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/28.%20Inverter%20Specific%20Yield%20at%20Block.mp4 | Hardik |  | 0.75 | 3 | 2021-10-30 | Pass |  | Mihir Patel | 2021-11-06 | 0.75 | 3 | Partially Passed | ICNOC-1059 ICNOC-1060 ICNOC-1246 |  |  |  | To be extended to the logical grouping | not visible
8 | Inverter PR | Solar | 4 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In KPI tab, from Asset Explorer section In Solar Power Plants -select any block of the particular plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Inverter PR" from Thumbnails 7. Click on Run |  | Not able to see it at block level | Hardik |  | 0.75 | 3 | 2021-10-30 | Pass | ICNOC-1135 | Aaron Kalisha | 2021-11-06 | 0.75 | 3 | Partially Passed | ICNOC-1062 |  |  |  | To be extended to the logical grouping | not visible
9 | String PR deviation histogram (Median - top 10 performing strings) | Solar | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In KPI tab, from Asset Explorer section In Solar Power Plants -select the block of the plant with string inverters 4. Click on Catalog 5. Select the date range 6.Select mentioned "String PR deviation band" from Thumbnails 7. Click on Run |  | Not able to see it at block level | Hardik |  | 0.75 | 15 | 2021-10-30 | Pass | ICNOC-1135 | Aaron Kalisha | 2021-11-06 | 0.5 | 10 | Fail | ICNOC-1334 |  |  |  |  | 1. Count of the nos. of string should be available 2. With the click we should have the drill down which shows the location of the underperforming strings
10 | String PR | Solar | 4 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select any block of the particular plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "String PR" from Thumbnails 7. Click on Run |  | Not able to see it at block level | Hardik |  | 0.75 | 3 | 2021-10-30 | Pass | ICNOC-1135 | Aaron Kalisha | 2021-11-06 | 0.75 | 3 | Partially Passed | [5 empty] | not visible
11 | String Power trend | Solar | 4 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Solar Power Plants -select the Strings 4. Click on Catalog 5. Select the date range 6. Select 5 min granularity 7.Select mentioned "String Power trend" from Thumbnails 8. Click on Run | 1. Compare the data from the NOC string power tend with the sample wise data from site | Not able to see | Hardik |  | 0.75 | 3 | 2021-10-30 | Pass | ICNOC-1135 | Aaron Kalisha | 2021-11-06 | 0.5 | 2 | Fail | ICNOC-1333 |  |  |  |  | X-axis is missing and should be on the daily basis
| Wind |  |  | NA | NA
A. | Wind Monitoring Scope |  |  | NA | NA
1 | Tree view-Turbine, Site, Portfolio level monitoring in single dashboard | Wind | 40 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Portfolio Drill Down Screen 3. Select the plant which the user wants to drill down 4. Select the Block in case of solar and WTG in case of wind for which drill down is req. 5. Select the tag in the drill down screen which the user wants to see 6. Test the functionality of creating a Ticket using "Create Ticket" button 7. Test the functinality of landing to the Analysis Catalog using "Analysis" button |  | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/14.%20Tree%20view-Turbine,%20Site,%20Portfolio%20level%20monitoring%20in%20single%20dashboard.mp4 | Hardik |  | 0.75 | 30 | 2021-10-23 | Pass |  | Darshak | 2021-10-30 | 1 | 40 | Pass
2 | Turbine State and Low performing turbine display (Power Curve deficient, Pitch angle abnormalities, Wind rose abnormalities) | Wind | 40 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section in wind Plants -select any the WTG for the analysis 4. Click on Catalog 5. Select the date range 6.Select mentioned "Wind Power Curve " from Thumbnails 7. Select 10 minutes granularity 7. Click on Run 8. After analysing, click Reset 9. Select mentioned "Wind Rose" from Thumbnails 10: Click on Run | 1. Download the data from NOC and verify it with the business prepared Power curve report | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/15.%20Turbine%20State%20and%20Low%20performing%20turbine%20display.mp4 | Hardik |  | 0.75 | 30 | 2021-10-23 | Pass |  | Darshak | 2021-10-30 | 0.5 | 20 | Fail | ICNOC-1086 ICNOC-1171 | Platform
3 | Machine Availability Calculation turbine Wise, Site wise (PPA), Portfolio level | Wind | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Wind Power Plants -select the asset, Portfolio, Plant , WTG 4. Click on Catalog 5. Select the date range 6.Select mentioned "WTG Availability" from Thumbnails 8. Click on Run | 1. Verify the NOC data that can be downloaded from the graph and compare with the sitewise site MIS data for WTG Availability (%) | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/16.%20WTG%20Availability.mp4 | Hardik |  | 0.75 | 15 | 2021-10-23 | Pass |  | Kishan | 2021-10-30 | 0.75 | 15 | Partially Passed | ICNOC-1078 |  |  |  | To be extended to the logical grouping
4 | Internal Grid Availability calculation turbine Wise, Site wise (PPA), Portfolio level | Wind | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Wind Power Plants -select the asset, Portfolio, Plant , WTG (IGA is available for the plant having the access to BOP) 4. Click on Catalog 5. Select the date range 6.Select mentioned "Internal Grid Availability" from Thumbnails 8. Click on Run | 1. Verify the NOC data that can be downloaded from the graph and compare with the sitewise site MIS data for Internal Grid Availability (%) | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/31.%20Internal%20Grid%20Availability.mp4 | Hardik |  | 0.75 | 15 | 2021-10-30 | Pass | ICNOC-1216 | Rohit | 2021-11-06 | 0.5 | 10 | Fail | ICNOC-1079 ICNOC-1288 ICNOC-1292 ICNOC-1293 | Ready for Retest |  |  | To be extended to the logical grouping | When availability is down in graph, then related events should show in event time line. Internal availability should come for each & every plant. First we need to clear, is it internal line or Internal grid. Because internal grid contains ( USS, BOP, PSS). For internal grid, where we dont have access of the feeders & PSS then by default we can keep it 100%. Option should be available when event occurred related to feeder or PSS then same can be change and reflect in availability automatically.
5 | External Grid Availability calculation turbine Wise, Site wise (PPA), Portfolio level | Wind | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In KPI tab, from Asset Explorer section In Wind Power Plants -select the asset, Portfolio, Plant , WTG (EGA is available for the plant having the access to BOP) 4. Click on Catalog 5. Select the date range 6.Select mentioned "External Grid Availability" from Thumbnails 8. Click on Run | 1. Verify the NOC data that can be downloaded from the graph and compare with the sitewise site MIS data for External Grid Availability (%) | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/29.%20External%20Grid%20Availability%20-%20Wind.mp4 | Hardik |  | 0.75 | 15 | 2021-10-30 | Pass |  | Rohit | 2021-11-06 | 0.75 | 15 | Partially Passed | ICNOC-1080 ICNOC-1295 ICNOC-1296 |  |  |  | To be extended to the logical grouping | When availability is down in graph, then related events should show in event time line. External availability should come for each & every plant. For External grid, where we dont have access of the feeders & PSS then by default we can keep it 100%. Option should be available when event occurred related to feeder or PSS then same can be change and reflect in availability automatically. Data is not coming correct where we have access of substation.
6 | Resource Availability calculation turbine Wise, Site wise (PPA), Portfolio level | Wind | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Wind Power Plants -select the asset, Portfolio, Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Resource Availability" from Thumbnails 8. Click on Run | 1. Verify the NOC data that can be downloaded from the graph and compare with the sitewise site MIS data for Resource Availability (%) | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/30.%20Resource%20Availability.mp4 | Hardik |  | 0.75 | 15 | 2021-10-30 | Pass |  | Darshak | 2021-11-06 | 0.75 | 15 | Partially Passed | ICNOC-965 ICNOC-1244 ICNOC-1245 |  |  |  | To be extended to the logical grouping | Need to simplify and restructure the availability matrix for wind. Need to have the inputs from all business stake holders UAT steps should not include the WTG
7 | PLF Calculation, turbine Wise, Site wise (PPA), Portfolio level | Wind | 40 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In KPI tab, from Asset Explorer section In Wind Power Plants -select the asset, Portfolio, Plant , WTG 4. Click on Catalog 5. Select the date range 6.Select mentioned "CUF at Plant level" from Thumbnails 8. Click on Run | 1. Verify the NOC data that can be downloaded from the graph and compare with the sitewise site MIS data for CUF (%) | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/21.%20Wind%20CUF.mp4 | Hardik |  | 0.75 | 30 | 2021-10-30 | Pass |  | Sambit | 2021-11-06 | 1 | 40 | Pass | ICNOC-1039 ICNOC-1040 ICNOC-1042 |  |  |  | To be extended to the logical grouping
8 | Wind Speed Calculation turbine Wise, Site wise (PPA), Portfolio level for both | Wind | 40 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Wind Power Plants -select the asset, Portfolio, Plant , WTG 4. Click on Catalog 5. Select the date range 6.Select mentioned "Wind Speed" from Thumbnails 8. Click on Run | 1. Verify the NOC data that can be downloaded from the graph and compare with the sitewise site MIS data for Wind Speed (m/s) | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/17.%20Wind%20Speed.mp4 | Hardik |  | 0.75 | 30 | 2021-10-23 | Pass |  | Rohit | 2021-10-30 | 0.75 | 30 | Partially Passed | ICNOC-1043 ICNOC-1044 ICNOC-1185 |  |  |  | To be extended to the logical grouping
9 | Wind Availability turbine Wise, Site wise (PPA), Portfolio level | Wind | 40 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Wind Power Plants -select the asset, Portfolio, Plant , WTG 4. Click on Catalog 5. Select the date range 6.Select mentioned "Wind Availability" from Thumbnails 8. Click on Run | 1. Verify the NOC data that can be downloaded from the graph and compare with the sitewise site MIS data for Wind Availability (%) | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/18.%20Wind%20Availability.mp4 | Hardik |  | 0.75 | 30 | 2021-10-23 | Pass |  | Rohit | 2021-10-30 | 0.75 | 30 | Partially Passed | ICNOC-1188 |  |  |  | To be extended to the logical grouping
10 | Manual data uploading for controlling of calculation of M.A.,IGA, EGA,RA | Wind | 10 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
11 | Lull Hrs. calculation | Wind | 20 | MVP 02 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Wind Power Plants -select the asset, Portfolio, Plant , WTG 4. Click on Catalog 5. Select the date range 6.Select mentioned "Lull Hours" from Thumbnails 8. Click on Run |  | Not loading for past any month | Hardik |  | 0.5 | 10 | 2021-10-30 | Fail | ICNOC-1187 |  | 2021-11-06 |  | 0 |  | ICNOC-1049 |  |  |  | To be extended to the logical grouping
12 | SCADA data Availability Calculation | Solar | 20 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
13 | Monitoring of Nacelle Data:- Environmental Temp, Wind speed, Nacelle Cabinet temp. | Wind | 10 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Tags tab, from Asset Explorer section In Wind Power Plants -select any WTG (max. 150 asset) 4. Click on Tags 5. Select the date range (max 30 days) 6.Select the required tag 7. Click on Run 8.Verify the functionality of downloading the data in csv file 9.Verify the zoom (snip & zoom) in and reset zoom functionality | 1. Download and verify the data from the site TML file |  | Hardik |  | 0.5 | 5 | 2021-10-30 | Pass | ICNOC-1131 ICNOC-1140 |  | 2021-11-06 |  | 0 |  | ICNOC-1067 ICNON-1068 ICNOC-1069 |  |  |  | Available as a part of Tags in Analysis Catalog
14 | Monitoring of Generator Speed, Wind Direction, Yaw Position to North, Blade Position-Pitch Angle, Line Voltage, Line Frequency, Fault and Warning List, Active Power, Reactive Power, Environmental Temp., Nacelle Cabinet temp. and rotor lock position w.r.t individual turbine and comparison with other Turbines | Wind | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Tags tab, from Asset Explorer section In Wind Power Plants -select any WTG (max. 150 asset) 4. Click on Tags 5. Select the date range (max 30 days) 6.Select the required tag 7. Click on Run 8.Verify the functionality of downloading the data in csv file 9.Verify the zoom (snip & zoom) in and reset zoom functionality | 1. Download and verify the data from the site TML file |  | Hardik |  | 0.5 | 10 | 2021-10-30 | Pass | ICNOC-1131 |  | 2021-11-06 |  | 0 |  | ICNOC-974 ICNOC-976 ICNOC-977 ICNOC-978 ICNOC-979 ICNOC-980 ICNOC-982 ICNOC-983 ICNOC-984 ICNOC-985 ICNOC-986 ICNOC-987 ICNOC-989 |  |  |  | Available as a part of Tags in Analysis Catalog
15 | Monitoring of Gearbox- Main bearing temp., Oil input temp., Oil input pressure, Gear box oil tank temp and Level, max. Bearing Temp w.r.t individual turbine and comparison with other Turbines | Wind | 10 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Tags tab, from Asset Explorer section In Wind Power Plants -select any WTG (max. 150 asset) 4. Click on Tags 5. Select the date range (max 30 days) 6.Select the required tag 7. Click on Run 8.Verify the functionality of downloading the data in csv file 9.Verify the zoom (snip & zoom) in and reset zoom functionality | 1. Download and verify the data from the site TML file |  | Hardik |  | 0.5 | 5 | 2021-10-30 | Pass | ICNOC-1131 |  | 2021-11-06 |  | 0 |  | ICNOC-991 ICNOC-996 ICNOC-997 ICNOC-998 ICNOC-999 ICNOC-1000 |  |  |  | Available as a part of Tags in Analysis Catalog
16 | Monitoring of Rotor speed, Generator winding temp, Generator Drive and Non drive end bearing temp. Max Winding temp., Generator cooling temp. w.r.t individual turbine and comparison with other Turbines . | Wind | 40 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Tags tab, from Asset Explorer section In Wind Power Plants -select any WTG (max. 150 asset) 4. Click on Tags 5. Select the date range (max 30 days) 6.Select the required tag 7. Click on Run 8.Verify the functionality of downloading the data in csv file 9.Verify the zoom (snip & zoom) in and reset zoom functionality | 1. Download and verify the data from the site TML file |  | Hardik |  | 0.5 | 20 | 2021-10-30 | Pass | ICNOC-1131 |  | 2021-11-06 |  | 0 |  | ICNOC-1001 ICNOC-1002 ICNOC-1003 |  |  |  | Available as a part of Tags in Analysis Catalog
17 | Monitoring of Vibration data- Acceleration drive direction and Non dive direction w.r.t individual turbine and comparison with other Turbines . Acceleration data Peak to Peak | Wind | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Tags tab, from Asset Explorer section In Wind Power Plants -select any WTG (max. 150 asset) 4. Click on Tags 5. Select the date range (max 30 days) 6.Select the required tag 7. Click on Run 8.Verify the functionality of downloading the data in csv file 9.Verify the zoom (snip & zoom) in and reset zoom functionality | 1. Download and verify the data from the site TML file |  | Hardik |  | 0.5 | 10 | 2021-10-30 | Pass | ICNOC-1131 |  | 2021-11-06 |  | 0 |  | ICNOC-1020 |  |  |  | Available as a part of Tags in Analysis Catalog
18 | Monitoring of Converter data Grid Voltage Phase, Current, Power factor, Converter temp, active and reactive power w.r.t individual turbine and comparison with other Turbines . | Wind | 40 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Tags tab, from Asset Explorer section In Wind Power Plants -select any WTG (max. 150 asset) 4. Click on Tags 5. Select the date range (max 30 days) 6.Select the required tag 7. Click on Run 8.Verify the functionality of downloading the data in csv file 9.Verify the zoom (snip & zoom) in and reset zoom functionality | 1. Download and verify the data from the site TML file |  | Hardik |  | 0.5 | 20 | 2021-10-30 | Pass | ICNOC-1131 |  | 2021-11-06 |  | 0 |  | ICNOC-1087 |  |  |  | Available as a part of Tags in Analysis Catalog
19 | Monitoring of Transformer Oil temp, winding temp and Oil level | Wind | 10 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Tags tab, from Asset Explorer section In Wind Power Plants -select any WTG (max. 150 asset) 4. Click on Tags 5. Select the date range (max 30 days) 6.Select the required tag 7. Click on Run 8.Verify the functionality of downloading the data in csv file 9.Verify the zoom (snip & zoom) in and reset zoom functionality | 1. Download and verify the data from the site TML file |  | Hardik |  | 0.5 | 5 | 2021-10-30 | Pass | ICNOC-1131 |  | 2021-11-06 |  | 0 |  | ICNOC-953 ICNOC-954 |  |  |  | Available as a part of Tags in Analysis Catalog
20 | Trigger log Display ,record and comparison with other turbines of the same model | Wind | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Equipment Overview Screen 3. Select the wind plant from the Asset Hierarchy 4. Cick on WTG tab 5. Click on the WTG for which the user needs to drill down 6. Select from "Overview", "Tags", "Tickets & Alarms", "Performance", "Device Ranking" 7. "Performance" and "Device Ranking" would help the user to compare the WTG with other WTGs of the same plant 8. Under "Device Ranking", select the KPI for which WTG is to be compared along with the desired date range | 1. Verify the KPIs in the "Performance" and "Device Ranking" Tab with the site MIS |  | Hardik |  | 0.75 | 15 | 2021-10-23 | Pass |  | Kishan | 2021-10-30 | 0.5 | 10 | Fail | ICNOC-1204 ICNOC-1205 ICNOC-362 | Platform |  |  | Would b be part of PTD
21 | Pitch hydraulic pressure for all blades | Wind |  | NA | Not Required
22 | Hydraulic main pressure | Wind |  | NA | Not Required
23 | Azimuth angle | Wind |  | NA | Not Required
24 | Wind utilization factor (WUF) | Wind |  | NA | Not Required
B. | Wind Analytics Scope |  |  | NA | NA
1 | Generation loss due to breakdown | Wind | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Wind Power Plants -select the asset, Portfolio, Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Generation Loss due to breakdown" from Thumbnails 7. Click on Run |  | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/38.%20Gen%20loss%20due%20to%20breakdown.mp4 | Hardik |  | 0.75 | 15 | 2021-10-30 | Pass |  | Darshak | 2021-11-06 | 0.5 | 10 | Fail | ICNOC-949 ICNOC-1320 |  |  |  | To be extended to the logical grouping | BOP unavailability loss and grid unavailability loss is same. secondly, plant unavailability loss should be sum of BOP, Grid, WTG unavailability which is not happening.
2 | Generation loss due to grid unavailability | Wind | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Wind Power Plants -select the asset, Portfolio, Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Generation loss due to grid unavailability" from Thumbnails 7. Click on Run |  | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/39.%20Gen%20Loss%20due%20to%20Grid%20Unavailability%20for%20wind.mp4 | Hardik |  | 0.75 | 15 | 2021-10-30 | Pass |  | Darshak | 2021-11-06 | 0.5 | 10 | Fail | ICNOC-950 ICNOC-1322 ICNOC-1323 |  |  |  | To be extended to the logical grouping | For 20th Oct 2021, value is in negative (-100MWh), which seem incorrect require a check for dev end. 1. Not plotting data for more than 1 month 2. Downloaded sheet is not in sequential manner, it is sorting the data by date irrespective of the month (Seq: 1st Sep, 1st Oct..... 30 sep, 30 Oct so on)
3 | Generation loss during Data Unavailability | Wind |  | NA | Not Required
4 | Generation loss during load shedding | Wind | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Wind Power Plants -select the asset, Portfolio, Plant, WTG 4. Click on Catalog 5. Select the date range 6.Select mentioned "Generation loss due to grid curtailment" from Thumbnails 7. Click on Run | 1. Verify the NOC data that can be downloaded from the graph and compare with the sitewise MIS/DGR value for Generation Loss due to Grid Curtailment | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/32.%20Gen%20loss%20due%20to%20Grid%20Curtailment%20-%20Wind.mp4 | Hardik |  | 0.75 | 15 | 2021-10-30 | Pass |  | Subrat | 2021-11-06 | 0.75 | 15 | Partially Passed | ICNOC-960 |  |  |  | To be extended to the logical grouping
5 | Transmission loss | Wind | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Wind Power Plants -select the asset, Portfolio, Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Transmission Loss" from Thumbnails 7. Click on Run | 1. Verify the NOC data that can be downloaded from the graph and compare with the sitewise MIS/DGR value for 33kV and 220 kV Transmission Loss | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/33.%20Transmission%20Loss.mp4 | Hardik |  | 0.75 | 15 | 2021-10-30 | Pass |  | Rohan/Darshak | 2021-11-06 | 0.5 | 10 | Fail | ICNOC-1013 ICNOC-1254 |  |  |  | To be extended to the logical grouping
6 | Difference between internal lines and grid failure | Wind |  | NA | Not Required
7 | Generation loss due to weather condition | Wind |  | NA | Not Required
8 | Energy based availability calculation ( WTG wise, Plant wise, Group wise, Portfolio wise) | Wind | 20 | MVP 02 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In KPI tab, from Asset Explorer section In Wind Power Plants -select the asset, Portfolio, Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Energy based availability calculation" from Thumbnails 7. Click on Run |  | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/40.%20Energy%20Based%20Availability%20for%20Wind.mp4 | Hardik |  | 0.75 | 15 | 2021-10-30 | Pass |  | Rohit | 2021-11-06 | 0.5 | 10 | Fail | ICNOC-1321
9 | Time based availability, equipment wise availability ( WTG wise, Plant wise, Group wise, Portfolio wise)' | Wind | 40 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In KPI tab, from Asset Explorer section In Wind Power Plants -select the asset, Portfolio, Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "WTG / BOP /Grid / Plant Availability" from Thumbnails 7. Click on Run |  | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/41.%20Time%20based%20availability%20Wind.mp4 | Hardik |  | 0.75 | 30 | 2021-10-30 | Pass |  | Rohit | 2021-11-06 | 0.75 | 30 | Partially Passed | ICNOC-990 |  |  |  | To be extended to the logical grouping
10 | Loss due to power curve deviation/machine performance | Wind | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In KPI tab, from Asset Explorer section In Wind Power Plants -select the asset, Portfolio, Plant, WTG 4. Click on Catalog 5. Select the date range 6.Select mentioned "Loss due to Power Curve deviation" from Thumbnails 7. Click on Run | 1. Verify the NOC data that can be downloaded from the graph and compare with the sitewise MIS/DGR value for WTG Performance Loss | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/34.%20Loss%20due%20to%20Power%20Curve%20Deviation.mp4 | Hardik |  | 0.75 | 15 | 2021-10-30 | Pass |  | Tushar | 2021-11-06 | 0.75 | 15 | Partially Passed | ICNOC-994 |  |  |  | To be extended to the logical grouping
11 | Lost production factor | Wind | 20 | MVP 02 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Wind Power Plants -select the asset, Portfolio, Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Lost Production Factor" from Thumbnails 7. Click on Run |  |  | Hardik |  | 0.75 | 15 | 2021-10-30 | Pass |  | Kishan | 2021-11-06 | 0.75 | 15 | Partially Passed |  |  |  |  | To be extended to the logical grouping
12 | Generation loss due to grid curtailment | Wind | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Wind Power Plants -select the asset, Portfolio, Plant 4. Click on Catalog 5. Select the date range 6.Select mentioned "Generation loss due to grid curtailment" from Thumbnails 7. Click on Run |  |  | Hardik |  | 0.75 | 15 | 2021-10-30 | Pass |  | Kishan | 2021-11-06 | 0.75 | 15 | Partially Passed |  |  |  |  | To be extended to the logical grouping
13 | Generation loss due to turbine capacity curtailment | Wind | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Wind Power Plants -select the asset, Portfolio, Plant, WTG 4. Click on Catalog 5. Select the date range 6.Select mentioned "Generation loss due to WTG curtailment" from Thumbnails 7. Click on Run |  | Not able to see it in the analysis Catalog | Hardik |  | 0.5 | 10 | 2021-10-30 | Fail | ICNOC-1238 |  | 2021-11-06 |  | 0
14 | Heat Map for Turbine production | Wind | 10 | MVP 02 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Wind Power Plants -select the WTG/WTGs 4. Click on Catalog 5. Select the date range 6. For the single day, it must show the Active Power and for multiple days it must show the WTG Generation 7.Select mentioned "Heat Map for WTG Generation" from Thumbnails 8. Click on Run | 1. Download the data from the graph and compare it with the sample wise data of the same WTG TML file | Multiple issue like, chart is not loading completely, WTG name is not complete | Hardik |  | 0.5 | 5 | 2021-10-30 | Fail | ICNOC-1190 |  | 2021-11-06 |  | 0 |  | ICNOC-1010
15 | Loss due to resource shortfall | Wind | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Wind Power Plants -select the asset, Portfolio, Plant , WTG 4. Click on Catalog 5. Select the date range 6.Select mentioned "Loss due to resource shortfall" from Thumbnails 7. Click on Run | 1. Verify the NOC data that can be downloaded from the graph and compare with the sitewise MIS/DGR value for Loss due to wind unavailability | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/22.%20Loss%20due%20to%20Resource%20Shortfall.mp4 | Hardik |  | 0.75 | 15 | 2021-10-30 | Pass |  | Kishan | 2021-11-06 | 0.5 | 10 | Fail | ICNOC-1022 ICNOC-1297 |  |  |  | To be extended to the logical grouping
16 | Waterfall diagram considering the losses | Wind | 40 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Wind Power Plants -select the asset, Portfolio, Plant , WTG 4. Click on Catalog 5. Select the date range 6.Select mentioned "Wind CUF Bridge" from Thumbnails 7. Click on Run | 1. Verify the NOC data that can be downloaded from the graph and compare with the sitewise CUF Bridge data | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/35.%20Wind%20CUF%20Bridge.mp4 | Hardik |  | 0.75 | 30 | 2021-10-30 | Pass |  | Kishan | 2021-11-06 | 0.75 | 30 | Partially Passed | ICNOC-1063 ICNOC-1064 ICNOC-1066 ICNOC-1298
17 | Wind rose analysis | Wind | 40 | MVP 02 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Analysis tab, from Asset Explorer section In Wind Power Plants -select the asset WTG 4. Click on Catalog 5. Select the date range 6.Select mentioned "Wind Rose" from Thumbnails 8. Click on Run |  | Fundametally looks like the calculation issue | Hardik |  | 0 | 0 | 2021-11-13 | Fail | ICNOC-1191 |  | 2021-11-20 |  | 0 |  | ICNOC-1014 - Resolved
18 | Pitch Vs rpm curve | Wind | 20 | MVP 01 | In Prod | 1. Login to the NOC platform 2. Go to Analysis >> Analysis Catalog 3. Click the Analysis Tab 4. Select the WTG for which the analysis is required 5. Select the data range from the date selector 6. Select the lowest available granularity 7. Click on "Pitch vs RPM Curve" from thumbnails 8. Click on Run | 1. Download the data of Pitch vs RPM Curve from the graph and compare it with the sample wise data of the same WTG TML file | Granularity Issue | Hardik |  | 0.75 | 15 | 2021-10-30 | Pass | ICNOC-1159 | Darshak | 2021-11-06 | 0.5 | 10 | Fail | ICNOC-1324 |  |  |  | To be extended to the logical grouping | Data available and can plot the graph 1. downloaded data is without timestamp 2. On selection of the overall site, we are getting average data instead of WTG wise data 3. Downloaded file doesn’t have any asset/site name
19 | RPM vs power curve | Wind | 20 | MVP 01 | In Prod | 1. Login to the NOC platform 2. Go to Analysis >> Analysis Catalog 3. Click the Analysis Tab 4. Select the WTG for which the analysis is required 5. Select the data range from the date selector 6. Select the lowest available granularity 7. Click on "RPM vs Power Curve" from thumbnails 8. Click on Run | 1. Download the data of RPM vs Power Curve from the graph and compare it with the sample wise data of the same WTG TML file | Granularity Issue | Hardik |  | 0.75 | 15 | 2021-10-30 | Pass | ICNOC-1159 | Darshak | 2021-11-06 | 0.5 | 10 | Fail | ICNOC-951 ICNOC-1325 |  |  |  | To be extended to the logical grouping | 1. downloaded data is without timestamp 2. On selection of the overall site, we are getting average data instead of WTG wise data 3. Downloaded file doesn’t have any asset/site name 4. on portfolio selection no title/details are appearing in the plot or in downloaded file.
20 | Wind speed VS RPM curve | Wind | 20 | MVP 01 | In Prod | 1. Login to the NOC platform 2. Go to Analysis >> Analysis Catalog 3. Click the Analysis Tab 4. Select the WTG for which the analysis is required 5. Select the data range from the date selector 6. Select the lowest available granularity 7. Click on "Wind Speed vs RPM Curve" from thumbnails 8. Click on Run | 1. Download the data of Wind Speed vs RPM Curve from the graph and compare it with the sample wise data of the same WTG TML file | Granularity Issue | Hardik |  | 0.75 | 15 | 2021-10-30 | Pass | ICNOC-1159 | Darshak | 2021-11-06 | 0.5 | 10 | Fail | ICNOC-1052 ICNOC-1053 ICNOC-1326 |  |  |  | To be extended to the logical grouping | 1. at below legends are not displayed, and no option to select any specific site data. 2. downloaded data is without timestamp 3. On selection of the overall site, we are getting average data instead of WTG wise data 4. Downloaded file doesn’t have any asset/site name 5. on portfolio selection no title/details are appearing in the plot or in downloaded file.
21 | Wind speed Vs Power curve | Wind | 20 | MVP 01 | In Prod | 1. Login to the NOC platform 2. Go to Analysis >> Analysis Catalog 3. Click the Analysis Tab 4. Select the WTG for which the analysis is required 5. Select the data range from the date selector 6. Select the lowest available granularity 7. Click on "Wind Speed vs Power Curve" from thumbnails 8. Click on Run | 1. Download the data of Wind Speed vs Power Curve from the graph and compare it with the sample wise data of the same WTG TML file | Granularity Issue | Hardik |  | 0.75 | 15 | 2021-10-30 | Pass | ICNOC-1159 | Darshak | 2021-11-06 | 0.5 | 10 | Fail | ICNOC-1056 ICNOC-1057 ICNOC-1327 |  |  |  | To be extended to the logical grouping | 1. at below legends are not displayed, and no option to select any specific site data. 2. downloaded data is without timestamp 3. On selection of the overall site, we are getting average data instead of WTG wise data 4. Downloaded file doesn’t have any asset/site name 5. on portfolio selection no title/details are appearing in the plot or in downloaded file. 6. Plot is not correct 7. X axes showing NONE values. 8. Windspeed is showing on X axes, but it's actually plotted on Y axes.
22 | Wind speed Vs pitch angle | Wind | 20 | MVP 01 | In Prod | 1. Login to the NOC platform 2. Go to Analysis >> Analysis Catalog 3. Click the Analysis Tab 4. Select the WTG for which the analysis is required 5. Select the data range from the date selector 6. Select the lowest available granularity 7. Click on "Wind Speed vs Pitch Angle" from thumbnails 8. Click on Run | 1. Download the data of Wind Speed vs Pitch Angle Curve from the graph and compare it with the sample wise data of the same WTG TML file | Granularity Issue | Hardik |  | 0.75 | 15 | 2021-10-30 | Pass | ICNOC-1159 | Darshak | 2021-11-06 | 0.5 | 10 | Fail | ICNOC-1054 ICNOC-1055 ICNOC-1329 |  |  |  | To be extended to the logical grouping | 1. at below legends are not displayed, and no option to select any specific site data. 2. downloaded data is without timestamp 3. On selection of the overall site, we are getting average data instead of WTG wise data 4. Downloaded file doesn’t have any asset/site name 5. on portfolio selection no title/details are appearing in the plot or in downloaded file. 6. Plot is not correct 7. X axes showing date values. 8. Windspeed is showing on X axes, but it's actually plotted on Y axes.
23 | Grouping Flexibility (Comparison of KPI Site wise/Cluster wise etc.) | Wind | 40 | MVP 01 | In Prod | 1. Login with accepted credentials for NOC Portal. 2.From Left Navigation bar in Analysis section click on Analysis Catalog screen 3 By default the date would be of present day and based on this day the graph will be shown 4.User can also change the date range in Date filter present on the page 5. By default KPI section will get open and user will select options from dropdown present in Asset Explorer section The user can select by expanding AGEL for eg: expand wind pant MUNDRA then Expand WTG then select any of the WTG or multiple WTGs of choice which needs to be compared 6. Click on Catalog option on top left 7.Select any of the Thumbnail of graph for eg: Total Generation present in the catalog section, The Run button will enable only when user will select the thumbnail 8.Click on Run Button and the user will be able to see the selected thumbnail graph for the selected asset in Asset Explorer on right side of the page 9.Repeat these steps for all other KPIs,assets and catalogs present here for different plants, logical grouping levels |  |  | Hardik |  | 0.75 | 30 | 2021-10-30 | Pass |  | Rohit | 2021-11-06 | 1 | 40 | Pass |  |  |  |  | To be extended to the logical grouping | 1. While selecting and deselecting, the no. of clicks should be minimal. For example, while reseting, at the first step all the checks should go away and then if the user resets again then the hierrachy should collapse.
24 | Revenue budget vs Actual | Wind | 40 | MVP 01 | In Prod | 1. Login to the NOC platform 2. Go to Analysis >> Analysis Catalog 3. Click the Analysis Tab 4. Select the Portfolio/State/SPV/Plant for which the analysis is required 5. Select the data range from the date selector 6. Select the lowest available granularity 7. Click on "Revenue Actual vs Budget" from thumbnails 8. Click on Run | 1. Download the data of the Revenue Budget vs Actual and compare it with the respective Site MIS |  | Hardik |  | 0.75 | 30 | 2021-10-30 | Pass |  | Kishan | 2021-11-06 | 0.75 | 30 | Partially Passed | ICNOC-952 ICNOC-1299 |  |  |  | To be extended to the logical grouping
25 | Bulk configuration (Analysis made on 1 turbine can be replicated on all turbines of plant, cluster & portfolio) | Wind | 40 | MVP 01 | In Prod | 1. Login with accepted credentials for NOC Portal. 2.From Left Navigation bar in Analysis section click on Analysis Catalog screen 3 By default the date would be of present day and based on this day the graph will be shown 4.User can also change the date range in Date filter present on the page 5. By default KPI section will get open and user will select options from dropdown present in Asset Explorer section The user can select by expanding AGEL for eg: expand wind pant MUNDRA then Expand WTG then select any of the WTG of choice 6. Click on Catalog option on top left 7.Select any of the Thumbnail of graph for eg: Total Generation present in the catalog section, The Run button will enable only when user will select the thumbnail 8.Click on Run Button and the user will be able to see the selected thumbnail graph for the selected asset in Asset Explorer on right side of the page 9.Repeat these steps for all other KPIs,assets and catalogs present here for different plants, logical grouping levels |  |  | Hardik |  | 0.75 | 30 | 2021-10-30 | Pass |  | Kishan | 2021-11-06 | 0.5 | 20 | Fail | ICNOC-1291 |  |  |  | Currently it is not user facing
26 | Requirement of User interface for controlling the Downtime reasons | Wind | 16 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
27 | Manual data uploading should be available (Data holes) | Wind | 20 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
28 | SCADA data availability | Wind | 8 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
C | Wind Predictive Analysis |  |  | NA | NA
1 | MTTR & MTBF | Wind | 40 | MVP 02 | In Prod | 1. Go to the Tickets Workspace from the navigation bar 2. Select last 30 days as the date range so that some tickets get populated 3. Go to the MTTR tab and select any plant in the MTTR panel 4. In the next panel select an equipment with one or more tickets shown in front of it 5. The MTTR for the equipment will be shown in the last panel (in case you don't see anything, click on "benchmark" below the graph to turn it off and rescale the graph to show only actual MTTR values 6. In the table below, scroll to the right to show the TTR column 7. Calculate the average TTR and compare with the TTR shown in the graph above |  |  | Utkarsh |  | 0.5 | 20 | 2021-11-27 | Yet to test |  |  | 2021-12-04 |  | 0 |  | ICNOC-1050
2 | Equipment / component temperature trend comparison | Wind | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Tags tab, from Asset Explorer section In Wind Power Plants -select any WTG (max. 150 asset) 4. Click on Tags 5. Select the date range (max 30 days) 6.Select the required tag 7. Click on Run 8.Verify the functionality of downloading the data in csv file 9.Verify the zoom (snip & zoom) in and reset zoom functionality |  |  | Hardik |  | 0.5 | 10 | 2021-10-30 | Pass | ICNOC-1131 |  | 2021-11-06 |  | 0 | [5 empty] | Would be covered in Tags section
3 | 5*5 matrix | Wind | 40 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
4 | Condition monitoring system - Vibration/alarm Analysis | Wind |  | NA | Not Required
D | SAP integration and Ticket Management |  |  | NA | NA
1 | SAP integration for PM module | Solar / Wind | 40 | MVP 01 | In Prod | 1. Login to NOC 2. Click on the Create Ticket top in the top header 3. Give a title to this ticket in the "Ticket Title" field 4. Select Ghani as plant 5. In the Search Asset drop-down, select "String_Inverters" and then click on the drop-down arrow again to select any of the listed inverter 6. Select ticket type as Maintenance 7. Verify all the fields that are pre-filled 8. Select Priority as "High Priority" 9. Select issue type from drop down 10. Provide Start Date and Time 11. Select Alarm Description from Drop Down 12. Provide ticket description 13. Once all mandatory information is entered, the Review and Submit button will be highlighted. Click on that and then in click on the Submit button 14. Once the confirmation message is displayed, log after 5 minutes into SAP PM module and check if the ticket is successfully created in SAP 15. Also log into Maventic app after 5 minutes and check if the ticket is succfully created on the Maventic app |  |  | Kamal |  | 0.5 | 20 | 2021-11-06 | Yet to test |  |  | 2021-11-13 |  | 0
2 | Notification for PM and BM and Assignments | Solar / Wind | 20 | MVP 01 | In Prod | Note: Preventive maintenance tickets are created in SAP PM, but these tickets can be seen in NOC. User can only create maintenance tickets for breakdown maintenance from NOC as detailed below 1. Go to any screen with the Create Ticket widget 2. Create a new test Maintenance ticket (not operational ticket) for any site / equipment of your choice 3. Go to the tickets workspace to verify that the new test ticket has been created 4. Contact the site team with access to Maventic for that site to check thier mobile app and confirm they can see the new test ticket |  |  | Utkarsh |  | 0.5 | 10 | 2021-11-13 | Yet to test |  |  | 2021-11-20 |  | 0
3 | Automatic Mail to Section in charge for turbine stopping more than 2 Hrs. | Wind | 20 | MVP 02 | In Prod | These notifications are configured, users need to conltac the program team (Utkarsh, Tapan, Hardik) to get their emails registered for notifications and they will start receiving emails anything a turbine has been down for 2 hours |  |  | Utkarsh |  | 0.5 | 10 | 2021-11-06 | Yet to test |  |  | 2021-11-13 |  | 0 | [5 empty] | Part of Workflow
E | API interface |  |  | NA | NA
1 | Wind pro data mapping | Wind |  | NA | Not Required
2 | Wind Speed Forecasting (3rd party integration) | Wind | 20 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | Enercast Integration
3 | Forecasting and scheduling mapping in the system | Solar / Wind | 20 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | Enercast Integration
4 | Comparison of Schedule Vs Actual Generation | Solar / Wind | 20 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | Enercast Integration
5 | Provision of integration of LIDAR system and Vibration Sensors. | Wind |  | NA | Not Required
6 | CCTV Operation Monitoring of Site if any installation | Solar / Wind |  | NA | Not Required
7 | Sub station monitoring | Solar / Wind |  | NA | Not Required
8 | Historical and real-time data access using API with functionality like weighted average, Realtime data. | Solar / Wind | 20 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
9 | File based bulk data sharing mechanism | Solar / Wind | 20 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
F | Reports |  |  | NA | NA
1 | KPI Summary (Site level and Portfolio level)- Estimated Vs Actual PLF, R.A., M.A (Time and Energy based), Wind Speed. | Wind | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Reports tab, from Asset Explorer section In Wind Power Plants -select the plant for which the report is required 4. Click on Report 5. Select the date range 6.Select mentioned "Wind Trend Report" from Thumbnails 7. Click on Run |  | Headers in the reports are not loading | Hardik |  | 0.75 | 15 | 2021-11-13 | Pass | ICNOC-1242 |  | 2021-11-20 |  | 0 |  | ICNOC-1076 |  |  |  | To be extended to the logical grouping
2 | Breakdown summary(Time & Energy Based) (Site level and Portfolio level):- WTG BM ,PM and Curtailment, Internal Grid shutdown, Fault, External Grid shutdown/Fault, ROW Hrs., project Shutdown, Predictive Shutdowns, Force Majeures. | Wind | 40 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | Would be part of Mgmt. Dashboard
3 | Pie Chart of the Breakdown summary- Month Wise, YTD | Wind | 20 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | Would be part of Mgmt. Dashboard
4 | Preventive Maintenance plan (Plan Vs Actual) | Solar / Wind |  | NA | Not Required
5 | Top 10 Breakdowns of the Plants | Solar / Wind | 20 | MVP 02 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Reports tab, from Asset Explorer section In Wind Power Plants -select the plant for which the report is required 4. Click on Report 5. Select the date range 6.Select mentioned "Top 10 Breakdown" from Thumbnails 7. Click on Run |  | Not able to see it for wind. For solar for some of the plants it is not loading | Hardik |  | 0 | 0 | 2021-11-20 | Fail | ICNOC-1239 |  | 2021-11-27 |  | 0 | [5 empty] | Would be part of Mgmt. Dashboard
6 | Details of Power Curve Deviation | Wind | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Reports tab, from Asset Explorer section In Wind Power Plants -select the WTG for which the report is required 4. Click on Report 5. Select the date range 6.Select mentioned "Power Curve Analysis" from Thumbnails 7. Click on Run |  | Random spikes in the reference curves | Hardik |  | 0.5 | 10 | 2021-11-20 | Fail | ICNOC-1145 |  | 2021-11-27 |  | 0
7 | MTTR & MTBF | Wind | 20 | MVP 01 | In Prod | 1. Go to the Tickets Workspace from the navigation bar 2. Select last 30 days as the date range so that some tickets get populated 3. Go to the MTTR tab and select any plant in the MTTR panel 4. In the next panel select an equipment with one or more tickets shown in front of it 5. The MTTR for the equipment will be shown in the last panel (in case you don't see anything, click on "benchmark" below the graph to turn it off and rescale the graph to show only actual MTTR values 6. In the table below, scroll to the right to show the TTR column 7. Calculate the average TTR and compare with the TTR shown in the graph above 8. The MTTR shown in the graph and the calculated average TTR should match each other |  |  | Utkarsh |  | 0.5 | 10 | 2021-11-27 | Yet to test |  |  | 2021-12-04 |  | 0
8 | Turbine 5*5 matrix | Wind | 20 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
9 | Top 10 Error | Wind |  | NA | Not Required
10 | Wind Speed Comp (Min, Max and Avg.) | Wind | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Reports tab, from Asset Explorer section In Wind Power Plants -select the plant for which the report is required 4. Click on Report 5. Select the date range 6.Select mentioned "Wind Trend Report" from Thumbnails 7. User would be able to see the section in the report which represents the wind speed (Min, Max and Avg.) 8. Click on Run | 1. Verify the NOC data that can be downloaded from the graph and compare with the sitewise sample data of wind speed | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/36.%20Min%20Max%20Avg%20Wind%20Speed%20in%20Report.mp4 | Hardik |  | 0.75 | 15 | 2021-10-30 | Pass |  | Darshak | 2021-11-06 | 0.5 | 10 | Fail | ICNOC-1278 | Need to discuss with business; for portfolio it should be part of Ph.2 |  |  | As a part of Wind Report
11 | Daily Site Status Mail with all KPIs / DGR | Solar / Wind | 40 | MVP 02 | In Prod |  |  |  | Hardik |  | 0.5 | 20 | 2021-11-27 | Yet to test |  |  | 2021-12-04 |  | 0 | [5 empty] | Testing in progress
12 | SCADA Connectivity Monitoring & Intimation if connectivity down | Solar / Wind | 20 | MVP 02 | In Prod | Note: IC NOC can only monitor the connectivity status with the gateway device. In our case this is N3uron. IC NOC does not have visibility to the underying SCADA / PLC / individual equipment status. To test the functionality for N3uron, follow the below steps: 1> Log-in to IC NOC and open Admin > Data Quality Overview screen and select the Communications tab 2> Select a plant which is currently showing Good connectivity. Make sure that Email notifications are enabled for this site in Role Based Access Control (RBAC) module 3> For this plant, disable the outbound communication from N3uron to IC. Make sure that SCADA to n3uron connectivity is disabled to prevent any data loss. Once the outbound communication is disabled, n3uron will start storing the data and waiting for connectivity to be restored. Not the time at which the outbound communication was stopped 4> Wait for 30 minutes and check the connectivity status in IC NOC. The status should now be "Bad" with a red dot 5> Check if email notification has been received for this event at the email addresses included in RBAC module 6> Enable the outbound communication form N3uron to IC (reverse of what we did in Step 3). N3uron will now start forwarding the old messages 7> After 30 minutes, go back to Communications tab. The communcation status for that plant will now be Good with a greed dot 8> Email notification will be generated again to inform the stakeholders about the restoration of communication with Plant |  |  | Kamal |  | 0.5 | 10 | 2021-11-06 | Yet to test |  |  | 2021-11-13 |  | 0 | [5 empty] | Intimation feature to be developed
13 | Notification assignments for breakdown activity | Solar / Wind | 40 | MVP 02 | In Prod | 1. Go to any screen with the Create Ticket widget 2. Create a new test Maintenance ticket (not operational ticket) for any site / equipment of your choice 3. Go to the tickets workspace to verify that the new test ticket has been created 4. Contact the site team with access to Maventic for that site to check thier mobile app and confirm they can see the new test ticket |  |  | Utkarsh |  | 0.5 | 20 | 2021-11-13 | Yet to test |  |  | 2021-11-20 |  | 0
14 | HWS and LWS Plan vs Actual Status | Wind |  | NA | Not Required
15 | STPT/Reliability Test Monitoring & Reports | Wind |  | NA | Not Required
G | Control |  |  | NA | NA
1 | Controlling of Wind turbines ( Option Required ) | Wind |  | NA | Not Required
| Common for wind & solar |  |  | NA | NA
1 | CXO dashboard requirement |  |  | NA | NA
| 1. Show top level KPIs, allow Min-Max range for KPIs and throw alert when limit is breached | Solar / Wind | 40 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0 |  | ICNOC-1072
| 2. Show a screen where-in every gain / loss is depicted in form of Rupee value | Solar / Wind | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Dashboard 3. Select Solar or Wind under management 4. Select the month 5. For the portfolio, under the "Portfolio Overview" tab, user can be able to see the Revenue Bridge where every loss or gain is depicted in form of Rupee 6. For the specific site, group of plant, SPV, RG or state, user can go to the "Site Details" and select the required plant/plants 7. User woud be able to see the Revenue Bridge where every loss or gain is depicted in form of Rupee |  | CUF Bridge and Revenue Bridge are not synch | Hardik |  | 0.5 | 10 | 2021-11-20 | Fail | ICNOC-1139 |  | 2021-11-27 |  | 0 |  | ICNOC-1073 ICNOC-1074 |  |  |  | It is a part of the revenue bridge
| 3. Aggregate data at site/cluster/state/SPV level / User defined group | Solar / Wind | 40 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Dashboard 3. Select Solar or Wind under management 4. Select the month 6. For the specific site, group of plant, SPV, RG or state, user can go to the "Site Details" and select the required plant/plants 7. User woud be able to see the all the CXO level KPIs aggregate at the selected level |  |  | Hardik |  | 0.75 | 30 | 2021-10-30 | Pass |  | Rohit | 2021-11-06 | 0.75 | 30 | Partially Passed | ICNOC-1075 |  |  |  | Part of the management dashboard
| 4. For all the KPIs we need the following aggregation MTD, QTD, Half yearly, YTD, LYSM, Trailing 12 months, Trailing 24 months | Solar / Wind | 40 | MVP 01 | In Prod |  |  |  | Hardik |  | 0.5 | 20 | 2021-11-27 | Yet to test |  |  | 2021-12-04 |  | 0 |  | ICNOC-1070
| 5. Drill down feature to the last level for all users | Solar / Wind | 40 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Portfolio Drill Down Screen 3. Select the plant which the user wants to drill down 4. Select the Block in case of solar and WTG in case of wind for which drill down is req. 5. Select the tag in the drill down screen which the user wants to see 6. Test the functionality of creating a Ticket using "Create Ticket" button 7. Test the functinality of landing to the Analysis Catalog using "Analysis" button |  |  | Hardik |  | 0.75 | 30 | 2021-10-23 | Pass |  | Darshak | 2021-10-30 | 0.5 | 20 | Fail | ICNOC-1170 | Ready for Retest
| 6. Ad-hoc reporting capabilities (Customizable reports from existing KPIs e.g. plant ranking, equipment performance etc.) | Solar / Wind | 20 | MVP 02 | In Prod |  |  |  | Hardik |  | 0.5 | 10 | 2021-11-27 | Yet to test |  |  | 2021-12-04 |  | 0 | [5 empty] | As a part of report composer
| 7. Slicing and dicing capabilities* within reports for e.g. | Solar / Wind | 20 | MVP 02 | In Prod |  |  |  | Hardik |  | 0.5 | 10 | 2021-11-27 | Yet to test |  |  | 2021-12-04 |  | 0 | [5 empty] | As a part of report composer
| a. Site ranking on specific parameters (operational, technical) | Solar / Wind | 20 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
| b. Performance of specific component | Solar / Wind | 20 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
| c. Top 20 attributes (monthly, quarterly, ytd etc) | Solar / Wind | 40 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
| Periodic refresh (frequency to be decided field wise / kpi wise) | Solar / Wind | 40 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
2 | Change in a breakdown type | Solar / Wind | 20 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
3 | Equipment level MTTR & MTBF calculation. | Solar / Wind | 20 | MVP 02 | In Prod | Based on ticket start and end time |  |  | Utkarsh |  | 0.5 | 10 | 2021-11-27 | Yet to test |  |  | 2021-12-04 |  | 0 |  | ICNOC-981
4 | Provision for uploading SOP, drawing | Solar / Wind | 20 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
5 | Rules to be made to distinguish between Data unavailability and erroneous data | Solar / Wind | 8 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | It is there as part of Data overview screen
6 | Analysis showing Data Availability | Solar / Wind | 20 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
7 | Ticket Management |  | - | NA | NA
| Tickets to be auto generated for every breakdown with the facility of auto assignment, auto escalation. | Solar / Wind | 20 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
| Tickets to be auto generated for performance deviation with the facility of auto assignment and auto escalation | Solar / Wind | 20 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
| SAP Integration for PM & MM module | Solar / Wind | 40 | MVP 02 | In Prod | 1. Login to NOC 2. Click on the Create Ticket top in the top header 3. Give a title to this ticket in the "Ticket Title" field 4. Select Ghani as plant 5. In the Search Asset drop-down, select "String_Inverters" and then click on the drop-down arrow again to select any of the listed inverter 6. Select ticket type as Maintenance 7. Verify all the fields that are pre-filled 8. Select Priority as "High Priority" 9. Select issue type from drop down 10. Provide Start Date and Time 11. Select Alarm Description from Drop Down 12. Provide ticket description 13. Once all mandatory information is entered, the Review and Submit button will be highlighted. Click on that and then in click on the Submit button 14. Once the confirmation message is displayed, log after 5 minutes into SAP PM module and check if the ticket is successfully created in SAP 15. Also log into Maventic app after 5 minutes and check if the ticket is succfully created on the Maventic app Note: SAP MM module integration is NOT in scope of AGEL IC NOC Phase 1. This will be taken up in future phases once the business requirements are defined |  |  | Kamal |  | 0.5 | 20 | 2021-11-13 | Yet to test |  |  | 2021-11-20 |  | 0
8 | Auto Report Generation |  |  | NA | NA
| Auto Reports to be generated of all the analysis mentioned above as per user requirement on monthly/weekly basis | Solar / Wind | 40 | MVP 02 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Reports tab, from Asset Explorer section In Solar Power Plants -select the plant 4. Click on Report 5. Select the date range 6.Select mentioned required report from Thumbnails that are created automatically 7. Click on Run List of automated report for solar 1. DGR 2. Inverter PR Analysis 3. Inverter, SAT & WMS Report 4. Solar Trend Report 5. Alarms Report 6. Late Awakening & Early Sleeping Inverter 7. Top 10 Breakdown List of automated report for wind 1. DGR 2. Power Curve 3. Wind Trend Report 4. Alarms Report |  |  | Hardik |  | 0.75 | 30 | 2021-10-30 | Pass |  | Rohit | 2021-11-06 | 0.5 | 20 | Fail | ICNOC-1328
9 | Audible notification for new alerts/events and persistent audible alarm for critical alerts | Solar / Wind | 20 | MVP 02 | In Prod | 1. Login to NOC 2. While user is on the platform on any of the screen, user would be able to see and hear the audible notifications for all the new alerts/events and alarms 3. User should be able to clear all the notifications at once click. 4. For further more information, user can click the "Bell" icon on the top bar 5. User must be able to see the alerts in the buckets of "Events", "Tickets", "Analytics" & "Others" 6. From the settings icon, user can select the Notification history for last 7 days, 30 days and 6 monhts 7. User can see the "Read" and "Unread" messages/alerts 8. User can also "Mark as Read for Me" |  |  | Hardik |  | 0.75 | 15 | 2021-10-30 | Pass |  | Kishan | 2021-11-06 | 0.75 | 15 | Partially Passed | ICNOC-1289 ICNOC-1287
10 | Monitoring rules with multiple conditions | Solar / Wind | 20 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
11 | Scheduled table tilting, module cleaning, grass cutting tickets | Solar | 20 | MVP 02 | In Prod |  |  |  | Hardik |  | 0.5 | 10 | 2021-11-27 | Yet to test |  |  | 2021-12-04 |  | 0
12 | Direct triggers to respective vendor in-case of repetitive faults at site on regular basis | Solar / Wind |  | NA | Not Required
13 | CCR Display - Dark Theme | Solar / Wind | 8 | MVP 01 | In Prod | 1. Login to NOC 2. Taggle between Dark & Light mode to check the functionality of dark mode | - | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/20.%20Dark%20Mode.mp4 | Hardik |  | 1 | 8 | 2021-10-23 | Pass |  | Sambit | 2021-10-30 | 1 | 8 | Pass
14 | Inverter PR Analysis at CTR/Plant Level including all inverters | Solar | 20 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In Reports tab, from Asset Explorer section In Solar Power Plants -select the plant for which the report is required 4. Click on Report 5. Select the date range 6.Select mentioned "Inverter PR Analysis at CTR/Plant Level including all inverters" from Thumbnails 7. Click on Run 8. The report would be downloaded in the excel format for the user |  | Only available for Ghani and Jhansi plant | Hardik |  | 0.5 | 10 | 2021-11-20 | Fail |  |  | 2021-11-27 |  | 0 |  | ICNOC-1077
15 | Provision to enter Budget values for daily, monthly & yearly figures | Solar / Wind | 20 | MVP 01 | In Prod | 1. Login to NOC 2. GO to Admin section 3. Click Budget Data Manager Tab 4. Click "Upload Budget Data" 5. Select the FY for which Budget data is to be uploaded 6. Select Budget Type 7. Browse the NOC template excel budget sheet that needs to be uploaded 8. Press Select, Preview or Cancel for appropriate action | 1. Once the file is uploaded, please check and verify with the actual budget sheet no. PLEASE BE CAUTIOUS WHEN EXECUTING THIS TEST CASE, AS THIS WOULD ALTER THE BUDGET NOS. AND RESPECTIVE KPI's DEPENDENT ON BUDGET NOS. | https://adaniltd.sharepoint.com/sites/AdaniIndustryCloud/Shared%20Documents/General/UAT%20Plan/Video%20Recordings/19.%20Budget%20Data%20Manager.mp4 | Hardik |  | 1 | 20 | 2021-10-23 | Pass |  | Rohit | 2021-10-30 | 0.5 | 10 | Fail | ICNOC-1186 | Platform
16 | We require different KPI views for CI and SI plants based on levels - Inverter type wise - Technology wise - Module type wise - Plant wise - Group wise - State wise - Company wise - etc. | Solar |  | NA | Not Required
17 | Remark marking on analysis for each inverter | Solar | 20 | MVP 02 | In Prod | 1. Login to NOC 2. Go to Analysis Catalog from left navigation bar 3. In KPI/Analysis tab, from Asset Explorer section In Solar/Wind Power Plants -select any component 4. Click on KPI/Analysis 5. Select the date range 6.Select the KPI/Analysis 7. Click on Run 8. At the bottom you should be able to see the events and post any comments on which other users can put their observations and thoughts | - |  | Hardik |  | 1 | 20 | 2021-10-23 | Pass |  | Mihir | 2021-10-30 | 1 | 20 | Pass
18 | All strings/inverters fault indication on plant array layout, so user can easily identify location of faults, rectify and validate same. | Solar | 20 | MVP 02 | In Prod | 1.Login to NOC. 2. Select the solar plant from the asset hierarchy 3.User is able to see the following on the right side- a.Create Ticket b.Asset Hierarchy c.Notification center. User is able to navigate to solar Photovoltaic under Monitoring. User is able to see the solar photovoltaic map in 2 views- a.Satellite View. b.2D Layout View(CAD) 3. User on clicking these views is able to see them accordingly. 4. Select Solar 2D layout -> Select Block / Inverter from bottom left drop-down 6. Check the Alarms box to see the alarms on the layout 5.Verify across Plant array layout view , All strings/inverters fault indication should be present so user can easily identify location of faults, rectify and validate same. |  |  | Hardik |  | 0.5 | 10 | 2021-11-20 | Yet to test |  |  | 2021-11-27 |  | 0 | [5 empty] | As a part of plant 2D layout
19 | Automatic ticket creation for all faulty / low performing strings, inverters, AC equipment's, etc. | Solar | 20 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
20 | Site wise user / technician level ticket distribution based on work load allocation, SLA monitoring | Solar / Wind | 20 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
21 | Plant raw data export and restoration in Adani Data Lake | Solar / Wind | 40 | MVP 02 | In Prod | This is currently a back-end functionality in IC NOC and will be done via email request. Follow the steps below: 1> For any plant where the raw data is needed, send an email to "hardik.bhesaniya@adani.com" with name of the plant and start-date and end-date for raw data export 2> Adani IC team, will then extract the raw data in CSV format for all the tags associated with the plant between the given date range. This is assuming the plant was on-boarded to IC NOC for that time period 3> The data in CSV format can then be easily restored in any other data base / lake etc. |  |  | Kamal |  | 0.5 | 20 | 2021-11-27 | Yet to test |  |  | 2021-12-04 |  | 0
22 | List of equipment sorted by low performance, fault, ranking, fault count for each plant a. Strings b. Inverters c. AC equipment's | Solar |  | NA | Not Required
23 | Inverter wise clipping loss notification | Solar |  | NA | Not Required
24 | Inverter PR deviation going beyond 5% and consolidated list of inverters email to respective team on daily basis | Solar | 20 | MVP 02 | In Prod | 1. Go to the mail box 2. Users added to the DL would be getting the daily mail in the morning with the subject line " Inverter PR Deviation Going Beyond 5%" 3. Open the attached excel sheet 4. Sheet contains the Plant Name, Name of the inverter deviating beyond 5%, its actual PR and the average PR of the plant with which it is being compared. | 1. Compare the inverter PR which is deviating beyond 5% with the inverter PR from the respective site MIS |  | Hardik |  | 0.5 | 10 | 2021-11-06 | Pass |  |  | 2021-11-13 |  | 0
25 | All modules / features availability on Mobile, e.g. plant / equipment monitoring, basic analysis, fault location indication Geo map, etc. | Solar / Wind | 40 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
26 | Role based Multiple dashboard, Multiple dashboard for each user | Solar / Wind | 40 | MVP 01 | In Prod | 1. Login to NOC 2. Go to Admin section 3. Click on User Management 4. Click on Users 5. Select the user for which access is to be provided or removed for any particular screen 6. Search and add the policy based on the user role | WE CAN DO THE LIVE DEMO WHERE WE CAN ADD / REMOVE ACCESS OF SOME OF THE BUSINESS USER, TO SEE THE CHANGES ON THE NOC PLATFORM |  | Hardik |  | 1 | 40 | 2021-10-23 | Pass |  | Darshak | 2021-10-30 | 0.5 | 20 | Fail |  |  |  |  | As a part of RBAM
27 | Inverter performance is going 3% of past 3 days average, consolidated list of inverters email to respective team on daily basis | Solar | 20 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
28 | Events display and report shall have following 1. Site specific identification of repetitive failure (e.g. IDT failure type wise occurring at portfolio) 2. MTBF and MTTR of every failure 3. Event shall have RCA (Route Cause analysis) and CAPA (Corrective action & Preventive action) form where user fills details for every kind of event and he can also decide not to submit any RCA / CAPA if that event is not related. 4. Results of Events failure count, MTTR, MTBF, RCA, CAPA, type wise events, etc. shall be visible at portfolio, site & plant level with MTD and YTD resolution. | Solar | 40 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
29 | Ticket report creation based on following - Issue type - Criticality - Technician wise - Company/contractor wise - Plant wise - Site wise - Portfolio wise | Solar / Wind | 40 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
30 | Automatic document attachment to ticket as per equipment, so technician can access related documents easily - SOP - Troubleshooting steps - Troubleshooting / system Manuals - Wiring / connection diagrams | Solar / Wind |  | NA | NA
32 | Platform shall able to handle more than 5 M tags/5 min, however there should be also provision to handle tags at 1 sec or lesser interval | Solar / Wind | 20 | MVP 01 | In Prod | 1. As per GCP at https://cloud.google.com/iot/quotas, per MQTT connection 100 messages can be received per second 2. Typically 1 n3uron node acts as one MQTT device connected to GCP. Each n3uron node can handle up to 25000 tags. 3. @ 5 minute data transmission frequency is 5 minutes, this is about 83 messages per second maximum. 4. Also as per GCP documentation above, there is no limit to number of devices that can be connected to the IC NOC. As such it is quite possible to scale up to 5 million tags and beyond 5. We can also easily handle data flowing in at much faster frequency of 1 sec or lower by configuring the n3uron nodes. |  |  | Kamal |  | 0.5 | 10 | 2021-11-27 | Yet to test | Dependent on Performance Load Testing |  | 2021-12-04 |  | 0
33 | Provide high level software architecture with component such as Database, OPC, Cloud setup, Micro services. | Solar / Wind |  | NA | NA
34 | Platform performance criteria such as latency, refresh rate | Solar / Wind | 40 | MVP 02 | In Prod | Covered as a part of the system performance (load) testing |  |  | Pankaj |  | 0.5 | 20 | 2021-11-27 | Yet to test | Dependent on Performance Load Testing |  | 2021-12-04 |  | 0 | [5 empty] | Can be fully dev when TSDB is implemented | Stress test need to be conducted. Performance can be better evaluated once all the sites are on-boarded
35 | What is Data reading frequency min to max (e.g. 30ms, 100ms, 1000s, 1 min, 5 min, 10 min, etc.)? | Solar / Wind |  | NA | NA
36 | Is it possible to have weather corrected P50, P75 or P90 numbers indication using Pvsyst data integration and modeling | Solar | 20 | Phase 2 | Phase 2 | [6 empty] | 0 | [6 empty] | 0
37 | Is it possible to calculate residual life assessment of equipment (e.g. Turbines, Inverters, transformers, etc.) | Solar / Wind |  | NA | NA
38 | Is your ticket management module is capable to integrate with SAP PM and MM module, so user can see all relevant activities / work flow for that ticket on platform without going into SAP? | Solar / Wind | 20 | MVP 01 | In Prod | 1. Log-in to NOC and create a Maintenance Ticket for any asset by clicking Create Ticket button and filling in the mandatory fields. Wait for confirmation from NOC for successful ticket creation 2. Go to the Tickets Workspace screen and locate the ticket just created. Click on the view button to see the details of ticket just created. The table should show status as "Open" indicating notification just created. User cannot work on a notification unless it is Approved 3. Go to either SAP or Maventic field app with right role and approve the ticket. Only once the notification is approved, it can be worked upon by the Site engineer 4. After 10 minutes, log back in NOC. The status of ticket should now be "Approved". Open the ticket in view mode and go to the History tab. 5. Verify that the history tab has entries corresponding to both Open and Approved status with relevant details such as time, source, updated by, assigned to 6. Log in again and update the status of ticket from Accepted to Completed and verify the the corresponding changes and also visible in NOC as described in step 5 above 7. From the Maventic app, attach a document or an image to the ticket. Verify that the attachment is accesible from NOC tickets detail view popup |  |  | Utkarsh |  | 0.5 | 10 | 2021-11-20 | Yet to test |  |  | 2021-11-27 |  | 0
39 | Are there any Machine Learning / Artificial intelligence tools available on your platform? | Solar / Wind |  | NA | NA
40 | Is there possibility to exchange data to any third party ML/AI platform to collect data from your platform and then write back results to show on your platform dashboard? | Solar / Wind |  | NA | NA
41 | Is it possible to have various level CXO dashboards? | Solar / Wind |  | NA | NA
Yes
No
User Configurable
Vendor Configurable
To be developed
Available
Not Available

## Progress
Team | Available to Test | Tested | Yet to Test | Pass | Fail | % Pass | % Fail |  | Team | Total Marks | Offered for UAT Marks
IC Team | 122 | 96 | 26 | 83 | 13 | 86.46% | 13.54% |  | IC Team | 2590
BU Team | 83 | 69 | 14 | 45 | 24 | 65.22% | 34.78% |  | BU Team | 2590
Team | Available to Test | Tested | Yet to Test | Pass | Fail | Partial Pass | Pass | Fail |  |  | Team | Pass | Fail | Yet to Test | Total | Total Marks | Marks Obtained | % Marks
IC Team | 2590 | 1908 | 682 | 1260 | 69 | 66.04% | 48.65% | 3.616% |  |  | IC Team | 83 | 13 | 26 | 122 | 2590 | 1670 | 64.48%
BU Team | [10 empty] | BU Team | 45 | 24 | 14 | 83 | 2590 | 937 | 36.18%
|  | 83 | [8 empty] | Ready for Retest |  | 0
Rohit
Darshak

## Daily Progress
| Adani Project |  |  |  |  | Adani BU
| UAT A Date | % Tested | % Passed | % Failed | % Yet to Test | UAT A Date | % Tested | % Passed | % Failed | % Yet to Test
| 2021-11-07 | 78.69% | 56.56% | 22.13% | 21.31% | 2021-11-07 | 56.56% | 36.89% | 19.67% | 43.44%
| 2021-11-08 | 78.69% | 68.03% | 10.66% | 21.31% | 2021-11-08 | 56.56% | 36.89% | 19.67% | 43.44%
| 2021-11-09 |  |  |  |  | 2021-11-09
| 2021-11-10 |  |  |  |  | 2021-11-10
| 2021-11-11 |  |  |  |  | 2021-11-11
MIS Freeze | 2021-11-12 |  |  |  |  | 2021-11-12
| 2021-11-13 |  |  |  |  | 2021-11-13
| 2021-11-14 |  |  |  |  | 2021-11-14
| 2021-11-15 |  |  |  |  | 2021-11-15
| 2021-11-16 |  |  |  |  | 2021-11-16
| 2021-11-17 |  |  |  |  | 2021-11-17
| 2021-11-18 |  |  |  |  | 2021-11-18
MIS Freeze | 2021-11-19 |  |  |  |  | 2021-11-19
| 2021-11-20 |  |  |  |  | 2021-11-20
| 2021-11-21 |  |  |  |  | 2021-11-21
| 2021-11-22 |  |  |  |  | 2021-11-22
| 2021-11-23 |  |  |  |  | 2021-11-23
| 2021-11-24 |  |  |  |  | 2021-11-24
| 2021-11-25 |  |  |  |  | 2021-11-25
MIS Freeze | 2021-11-26 |  |  |  |  | 2021-11-26
| 2021-11-27 |  |  |  |  | 2021-11-27
| 2021-11-28 |  |  |  |  | 2021-11-28
| 2021-11-29 |  |  |  |  | 2021-11-29
| 2021-11-30 |  |  |  |  | 2021-11-30

## summary (hidden)
Total Line Items | [5 empty] | Maximum marks |  |  |  |  | Marks Scored
Date | MVP 01 | MVP 02 | Phase 2 | Total |  | Date | MVP 01 | MVP 02 | Phase 2 | Total | Date | MVP 01 | MVP 02 | Phase 2 | Total
2021-10-11 | 0 | 0 | 0 | 0 |  | 2021-10-11 | 0 | 0 | 0 | 0 | 2021-10-11 | 0 | 0 | 0 | 0 | #DIV/0!
2021-10-18 | 0 | 0 | 0 | 0 |  | 2021-10-18 | 0 | 0 | 0 | 0 | 2021-10-18 | 0 | 0 | 0 | 0 | #DIV/0!
2021-10-25 | 0 | 0 | 0 | 0 |  | 2021-10-25 | 0 | 0 | 0 | 0 | 2021-10-25 | 0 | 0 | 0 | 0
2021-11-08 | 0 | 0 | 0 | 0 |  | 2021-11-08 | 0 | 0 | 0 | 0 | 2021-11-08 | 0 | 0 | 0 | 0
2021-12-31 | 0 | 0 | 0 | 0 |  | 2021-12-31 | 0 | 0 | 0 | 0 | 2021-12-31 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 |  | Total | 0 | 0 | 0 | 0 | Total | 0 | 0 | 0 | 0
Date | Phase 1 Marks Achieved | Marks % | Marks | % | Remarks
2021-09-29 | 957 | 36.95% | 957 | 36.95% |  |  | 2866
2021-10-06 | 957 | 36.95% | 957 | 36.95%
2021-10-11 | 957 | 36.95% | 1130 | 43.63% | Offered to BU to validate
2021-10-18 | 957 | 36.95%
2021-10-25 | 957 | 36.95%
2021-11-01 | 957 | 36.95%
2021-11-08 | 957 | 36.95%
2021-12-31 | 957 | 36.95%
Date | Phase 1 Marks Achieved | Marks % | Marks | % | Remarks
2021-09-29 | 957 | 28.17% | 957 | 26.73%
2021-10-06 | 957 | 28.17% | 957 | 26.73%
2021-10-11 | 957 | 28.17% | 1130 | 31.56% | Offered to BU to validate
2021-10-18 | 957 | 28.17%
2021-10-25 | 957 | 28.17%
2021-11-01 | 957 | 28.17%
2021-11-08 | 957 | 28.17%
2021-12-31 | 957 | 28.17%
Date | % Target Achievement | % achieved*
2021-09-29 | 28.17% | 26.73%
2021-10-06 | 28.17% | 26.73%
2021-10-11 | 28.17% | 31.56%
2021-10-18 | 28.17%
2021-10-25 | 28.17%
2021-11-01 | 28.17%
2021-11-08 | 28.17%
2021-12-31 | 28.17%
Formulas:
Total Line Items = [Total Line Items, row above]+7

## Phase 1 Maturity Plan (hidden)
| Baseline Marks | Current Marks | Baseline Marks % | Current Marks %
Date
2021-10-01 | 957
2021-10-08 | 957
2021-10-15 | 1239
2021-10-22 | 1972
2021-10-29 | 2392
2021-11-05 | 2392
2021-11-12
2021-11-19
2021-11-26
2021-12-03
2021-12-10
2021-12-17
2021-12-24
2021-12-31

## IC NOC summary (hidden)
Developed in BAX | (Multiple Items)
Feature Develpoment_ICNOC by AIC team | (Multiple Items)
IC NOC Item Status | (All)
Row Labels | Count of Class of KPI | Average of % Achievement | Average of FD% | Average of DP% | Average of UAT% | Average of RL%
Dev in Progress | 23 | 0% | 0% | 0% | 0% | 0%
F D - Specification Change | 8 | 25% | 35% | 32.5% | 0% | 32.5%
F D - Training Gap | 91 | 36.12% | 52.34% | 44.08% | 1.648% | 46.41%
Grand Total | 122 | 28.58% | 41.34% | 35.01% | 1.23% | 36.75%

## Reference (hidden)
Reference
F D - Training Gap
F D - Specification Change
F D - Data Issues
Dev in Progress
Gap in Dev
Out of Scope in Phase 1
Not Required
Aligned
Not in Prod

## FOR CALCULATION ONLY (hidden)
Row Labels
M1
M2
M3
M4
M5
(blank)
NO CATEGORY
POC/OPTION
Grand Total

## M1-M5 SCORECARD (hidden)
M1 | Completed | Pending | 0 | 0 | Grand Total (Excluding Not Required) | Marks (out of 100) | Weightage for M1-M5 (%) | Marks Excluding Product develop | Weightage (%)
M2 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 3 | #DIV/0! | 3
M3 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 10 | #DIV/0! | 10
M4 | 0 | 0 | 0 | 0 | 0
M5 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 55 | #DIV/0! | 55
(blank) | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 20 | 0 | 20
NO CATEGORY | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 5 | 0 | 5
Grand Total | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 5 | #DIV/0! | 5
0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 2 | #DIV/0! | 2
TOTAL | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! |  | #DIV/0!
JUST FOR REFERENCE
0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0

## FINAL SCORECARD (hidden)
SR. NO | ITEMS | SCORE | WEIGHTAGE
1 | M1-M5 IMPLEMENTATION | 90.56% | 80%
2 | ROLL OVER TO SITES | 100% | 10%
3 | UAT FOR ALL SITES | 0% | 10%
| FINAL SCORE (WITHOUT UAT) | 91.61%
| FINAL SCORE (WITH PENDING UAT) | 82.45%